## Cover
Proposed CAN DSLAMs
Issue 267
2021-03-02
External Distribution
The report is updated as required due to the small number of CAN DSLAMs being installed.
This report provides details of proposed CAN DSLAMs including TopHat IP DSLAMs.
Notes:-
Telstra reserves the right to alter DSLAM proposed rollout dates and to change individual DSLAMs in the rollout.
When available, the proposed service date and maps are provided.
TopHats could be used by Telstra to provide ADSL2+ port capacity at existing roadside cabinets. In most instances these provide additional capacity with the ADSL2+ports providing higher speeds replacing the existing ADSL ports. In other cases the TopHat upgrades will be used for a first-in ADSL installation.
It is possible that other DSLAM configurations may also be used
A "Y" in the "Spectrally Shaped or Attenuated" column indicates that the DSLAM utilises a Non-Deployment Class System as approved by Communication Alliance. Details can be found at http://www.commsalliance.com.au/Documents/Documents/codes/c559/ndcs. These non-deployment classes are used to minimise the effect of interference to exchange based ADSL services that are also being supplied to the CAN DSLAM service area.
Note that additional ports and speeds may not be available to all customers in the map areas due to other factors such as transmission loss and other network constraints.
ESA and DA Maps
The Maps remain Telstra Proprietary. However, TW Customers may download and/or print the maps for their own purpose only.
Whilst Telstra takes every effort to ensure the accuracy of these coverage maps, they should be used only as a guide. Only a Full Service Qualification will confirm whether ADSL can be provided to a particular FNN or address.

## Proposed CAN DSLAMs
Proposed CAN DSLAMs
Issue 267
2021-03-02
External Distribution
This and other DSL Reports and Plans can be found at:
http://telstrawholesale.com.au/products/broadband/adsl/adsl-reports-plans/index.htm
© Telstra Corporation Limited 2013.
State | ESA Name | ESA Code | Site ID | Existing DSLAM ID | Proposed DSLAM ID | Distribution Areas | Post Code | Proposed Service Date | Actual Service Date | Spectrally Shaped or Attenuated | ESA Map | DA Map 1 | DA Map 2 | DA Map 3 | DA Map 4 | DA Map 5 | DA Map 6 | Notes
QLD | ALBANY CREEK | ABCK | CA54 | QABCKE74M | QABCKE4006M | DA33; DA54 | 4037 | 2014-11-30 | 2014-09-01
NSW | ALBION PARK | ALPK | CA9 | QALPKE1S7 | QALPKE4004M | DA9 | 2529 | 2014-12-31 | 2014-11-19 |  | ALPK-CA9-Area-Layout.pdf | ALPK-CA9-Map-ALPK-DA9.pdf
WA | AMBERGATE | AMGT | CA1 | QAMGTE1S2 | QAMGTE4001M | DA2 | 6280 | 2013-12-31 | 2013-12-20 |  | AMGT-G1A-Area-Layout.pdf | AMGT-G1A-Map-AMGT-DA2.pdf
VIC | BACCHUS MARSH | BACC | P525 | QBACCE93M | QBACCE4003M | DA500 | 3340 | 2014-08-31 | 2014-07-31
QLD | MOOROOLBARK | BLHS | CA28 | QBLHSE21M | QBLHSE4007M | DA28 | 4017 | 2014-11-30 | 2014-10-22
WA | BALDIVIS | BALD | G47 | QBALDE4016M | QBALDE4006M | DA47 | 6171 | 2013-12-31 | 2013-12-20 |  | BALD-G47-Area-Layout.pdf | BALD-G47-Map-BALD-DA47.pdf
QLD | BEERWAH | BRWH | CA11 | QBRWHE13M | QBRWHE4001M | DA11; DA15 | 4519 | 2015-04-30 | 2015-03-17
QLD | BOHLE | BOHL | CA2 | QBOHLE13M | QBOHLE4006M | DA16; DA39 | 4814 | 2014-10-31 | 2014-09-15 |  | BOHL-CA2-Area-Layout.pdf | BOHL-CA2-Map-BOHL-DA39.pdf | BOHL-CA2-Map-BOHL-DA16.pdf
QLD | BUDERIM | BUDE | CA54 | QBUDEE17M | QBUDEE4014M | DA54; DA85 | 4556 | 2015-01-31 | 2014-12-17
QLD | CABOOLTURE | CABO | CA82 | New | QCABOE4015M | DA17; DA20; DA49 | 4510 | 2014-01-31 | 2014-01-16 |  | CABO-CA82-Area-Layout.pdf | CABO-CA82-Map-CABO-DA17.pdf | CABO-CA82-Map-CABO-DA20.pdf | CABO-CA82-Map-CABO-DA49.pdf
QLD | CALOUNDRA | CALO | CA68 | QCALOE15M | QCALOE4014M | DA68; DA38 | 4551 | 2014-07-31 | 2014-07-21 |  | CALO-CA68-Area-Layout.pdf | CALO-CA68-Map-CALO-DA68.pdf | CALO-CA68-Map-CALO-DA38.pdf
NSW | CASTLE HILL | CAST | CA36 | QCASTE4012M | QCASTE4027M | DA399; DA423 | 2154 | 2014-12-31 | 2014-11-21 |  | CAST-CA36-Area-Layout.pdf | CAST-CA36-Map-CAST-DA423.pdf | CAST-CA36-Map-CAST-DA399.pdf
Qld | COOMBABAH | CBBH | CA87 | QCBBHE4S5 | QCCBHE4006M | DA3 DA89 | 4216 | 2013-12-31 | 2013-12-18 |  | CBBH-CA87-Area-Layout.pdf | CBBH-CA87-Map-CBBH-DA3.pdf | CBBH-CA87-Map-CBBH-DA89.pdf
NSW | CORRIMAL | CORR | CA2 | QCORRE4013M | QCORRE4006M | DA93, DA56, DA66, DA71, DA54, DA55 | 2516 | 2014-12-31 | 2014-12-08 |  | CORR-CA2-Area-Layout.pdf | CORR-CA2-Map-CORR-DA56.pdf | CORR-CA2-Map-CORR-DA93.pdf | CORR-CA2-Map-CORR-DA71.pdf | CORR-CA2-Map-CORR-DA66.pdf | CORR-CA2-Map-CORR-DA54.pdf
WA | COTTESLOE | CTOE | P36 | N/A | QCTOEE4003M | DA36 | 6010 | 2014-08-31 | 2014-07-31 |  | CTOE-P36-Area-Layout.pdf | CTOE-P36-Map-CTOE-DA87.pdf | [5 empty] | CTOE DA55 is a proposed DA
NSW | COWPASTURES | CWPS | CA47 | QCWPSE4007M | QCWPSE4012M | DA47 | 2570 | 2014-06-30 | 2014-06-12
NSW | DAPTO | DAPO | CA2 | N/A | QDAPOE4007M | DA73 | 2530 | 2014-10-31 | 2014-10-31 |  | DAPO-CA2-Area-Layout.pdf | DAPO-CA2-Map-DAPO-DA2.pdf
QLD | EIGHT MILE PLAINS | EMPS | CA105 | N/A | QEMPSE4014M | DA105; DA94 | 4112 | 2014-06-30 | 2014-06-20 |  | EMPS-CA105-Area-Layout.pdf | EMPS-CA105-Map-EMPS-DA105.pdf | EMPS-CA105-Map-EMPS-DA94.pdf
QLD | EMERALD | EMER | G58 | QEMERE4002 | QEMERE4002M | DA58 | 4720 | 2014-11-30 | 2014-10-31 |  | FOER-CA59-Area-Layout.pdf | FOER-CA59-Map-FOER-DA32.pdf | FOER-CA59-Map-FOER-DA59.pdf
WA | FORRESTDALE | FTDL | G43 | QFTDLE1S7 | QTFDLE4007M | DA33; DA43 | 6112 | 2015-01-31 | 2014-12-08 |  | FTDL-G43-Area-Layout.pdf | FTDL-G43-Map-FTDL-DA33.pdf | [5 empty] | FTDL DA43 is a proposed DA
NSW | FORSTER | FOER | CA59 | QFOERE4008M | QFOERE4021M | DA59; DA32 | 2428 | 2015-10-31 | 2014-10-24
QLD | GOWRIE JUNCTION | GOWJ | CA10 | QGOWJE35M | QGOWJE4001M | DA7 | 4350 | 2015-01-31 | 2014-12-16
QLD | GRACEMERE | GRAC | G38 | QGRACE4002M | TBA | DA38 | 4702 | 2015-03-31 | 2015-02-27
Vic | HEIDELBERG | HDBG | CA38 | QHDBGE104M | QHDBGE4001M | DA240 | 3085 | 2013-08-31 | 2013-08-13
QLD | HIGHFIELDS | HFDS | CA39 | QHFDSE5S8 | QHFDSE4008M | DA38 | 4352 | 2014-09-30 | 2014-07-21 |  | HFDS-CA39-Area-Layout.pdf | HFDS-CA39-Map-HFDS-DA38.pdf
QLD | HIGHFIELDS | HFDS | CA22 | QHFDSE41M | QHFDSE4009M | DA11; DA25; DA26 | 4352 | 2015-03-31 | 2015-02-16
NSW | HINTON | HINT | CA05 | QHINTE4002M | QHINTE4004M | DA5; DA6 | 2320 | 2015-03-31 | 2015-02-10
NSW | INGLEBURN | INGL | CA18 | QINGLE1S4 | QINGLE4003M | DA150 | 2167 | 2014-02-28 | 2014-02-13 |  | INGL-CA18-Area-Layout.pdf | INGL-CA18-Map-INGL-DA150.pdf
NSW | JINDABYNE | JINJ | CA19 | QJINJE4003M | QJINJE4005M | DA18; DA19 | 2627 | 2014-10-31 | 2014-10-21 |  | JINJ-CA19-Area-Layout.pdf | JINJ-CA19-Map-JINJ-DA19.pdf | JINJ-CA19-Map-JINJ-DA18.pdf
QLD | KALLANGUR | KLGR | CA55 | QKLGRE50M | QKLGRE4029M | DA55 | 4503 | 2014-06-30 | 2014-06-12 |  | KLGR-CA55-Area-Layout.pdf | KLGR-CA55-Map-KLGR-DA55.pdf
NSW | KELLYVILLE | KELL | CA5 | QKELLE4016M | QKELLE4064M | DA5; DA6 | 2768 | 2015-12-31 | 2014-11-21 |  | KELL-CA5-Area-Layout.pdf | KELL-CA5-Map-KELL-DA6.pdf | KELL-CA5-Map-KELL-DA5.pdf
NSW | KELLYVILLE | KELL | CA8 | QKELLE4015M | QKELLE4065M | DA9; DA30 | 2155 | 2015-11-30 | 2014-12-16 |  | KELL-CA8-Area-Layout.pdf | KELL-CA8-Map-KELL-DA30.pdf | KELL-CA8-Map-KELL-DA9.pdf
QLD | KIRWAN | KIRN | CA25 | QKIRNE67S3 | QKIRNE4019M | DA784; DA788 | 4815 | 2013-11-30 | 2014-08-11 |  | KIRN-CA25-Area-Layout.pdf | KIRN-CA25-Map-KIRN-DA784.pdf | KIRN-CA25-Map-KIRN-DA788.pdf
NSW | KORORO | KORO | CA1 | QKOROE4003M | TBA | DA18 | 2450 | 2014-08-31 | 2014-08-08 |  | KORO-CA1-Area-Layout.pdf | KORO-CA1-Map-KORO-DA18.pdf
VIC | LAHARUM NORTH | LAMN |  | N/A | QLAMNE4001M | DA500 | 3401 | 2014-08-31 | 2014-06-20
WA | LANDSDALE | LDLE | DA53 | QLDLEE4013M | QLDLEE4013M | DA53 DA54 | 6065 | 2015-02-28 | 2015-02-04
VIC | LAVERTON | LTVN | G155 | QLTVNE24S5 | QLTVNE4009M | DA155 | 3027 | 2014-08-31 | 2014-03-25 |  | LTVN-G155-Area-Layout.pdf | LTVN-G155-Map-LTVN-DA155.pdf | LTVN-G155-Map-LTVN-DA158.pdf
NSW | MACKSVILLE | MACS | CA19 | QMACSE4001S3 | QMACSE4006M | DA19; DA17 | 2447 | 2014-10-31 | 2014-09-17 |  | MACS-CA19-Area-Layout.pdf | MACS-CA19-Map-MACS-DA17.pdf | MACS-CA19-Map-MACS-DA19.pdf
VIC | MERNDA | MRDA | CA18 | QMRDAE7S3 | QMRDAE4005M | DA38; DA64 | 3754 | 2014-04-30 | 2014-06-20
QLD | MIDDLE RIDGE | MIDD | CA113 | QMIDDE72M | QMIDDE4022M | DA51; DA117 | 4350 | 2015-01-31 | 2014-11-05
QLD | MISSION BEACH | MIBH | CA11 | new | QMIBHE4001M | DA11 | 4852 | 2013-11-30 | 2013-11-22
QLD | MOGGILL | MOGG | CA22 | QMOGGE31M | QMOGGE4005M | DA22 | 4069 | 2014-06-30 | 2014-06-16 |  | MOGG-CA22-Area-Layout.pdf | MOGG-CA22-Map-MOGG-DA22.pdf
VIC | MORNINGTON | MORN | CA24 | QMORNE36M | QMORNE4009M | DA91; DA98 | 3934 | 2014-07-31 | 2014-06-24 |  | MORN-CA24-Area-Layout.pdf | MORN-CA24-Map-MORN-DA91.pdf | MORN-CA24-Map-MORN-DA98.pdf
VIC | MORWELL | MWRL | CA6 | QMWRLE66M | QMWRLE4004M | DA69 | 3840 | 2014-07-31 | 2014-07-10 |  | MWRL-CA6-Area-Layout.pdf | MWRL-CA6-Map-MWRL-DA69.pdf
NSW | NEW LAMBTON | NLTN | CA124 | QNLTNE4011M | QNLTNE4025M | DA124 | 2305 | 2015-03-31 | 2015-02-12
NSW | NEW LAMBTON | NLTN | CA78 | QNLTNE4010M | QNLTNE4026M | DA78 | 2289 | 2015-03-31 | 2015-02-18
QLD | NEWTOWN | NEWO | CA79 | QNEWOE100M | QNEWOE4009M | DA79 | 4350 | 2015-01-31 | 2014-11-14
NSW | NOWRA | NWRA | CA1 | QNWRAE4015M | QNWRAE4015M | NA | 2541 | 2014-06-30 | 2014-06-13
NSW | NOWRA | NWRA | CA168 | QNWRAE4014M | QNWRAE4028M | DA59; DA61; DA169; DA60 | 2541 | 2015-01-31 | 2014-12-16 |  | NWRA-CA2-Area-Layout.pdf | NWRA-CA2-Map-NWRA-DA87.pdf | NWRA-CA2-Map-NWRA-DA66.pdf | NWRA-CA2-Map-NWRA-DA55.pdf
NSW | NOWRA | NWRA | CA2 | QNWRAE4025M | QNWRAE4029M | DA87; DA55; DA66 | 2541 | 2014-10-31 | 2014-10-22
QLD | ORMEAU | ORME | CA5 | QORMEE41M | QORMEE4008M | DA12; DA76 | 4208 | 2014-11-30 | 2014-11-30
NSW | PAMBULA | PAMB | CA8 | QPAMBE4001S2 | QPAMBE4007M | DA8 | 2549 | 2015-05-31 | 2015-04-29 |  | PAMB-CA8-Area-Layout.pdf | PAMB-CA8-Map-PAMB-DA8.pdf
NSW | PAMBULA | PAMB | CA7 | QPAMBE4001S4 | QPAMBE4006M | DA7 | 2549 | 2015-03-31 | 2015-01-30 |  | PAMB-CA7-Area-Layout.pdf | PAMB-CA7-Map-PAMB-DA7.pdf
QLD | PARKHURST | PARK | P6 | QPARKE59S3 | TBA | DA6; DA15 | 4701 | 2014-08-31 | 2014-07-28
QLD | PEREGIAN BAY | PRGN | CA14 | QPRGNE6M | QPRGNE4004M | DA14 | 4573 | 2015-01-31 | 2014-10-31
NSW | PICTON | PCTN | CA18 | QPCTNE4006M | QPCTNE4009M | DA4; DA18 | 2571 | 2014-10-31 | 2014-10-08
NSW | QUAK | QUAK | CA3 | QQUAKE4006M | QQUAKE4008M | DA22; DA127; DA128; DA129 | 2763 | 2014-10-31 | 2014-09-16 |  | PCTN-CA18-Area-Layout.pdf | PCTN-CA18-Map-PCTN-DA4.pdf | PCTN-CA18-Map-PCTN-DA18.pdf
QLD | REDLYNCH | RDLH | CA14 | QRDLHE1S2 | QRDLHE4006M | DA14; DA17; DA18 | 4870 | 2014-07-31 | 2014-07-03 |  | QUAK-CA3-Area-Layout.pdf | QUAK-CA3-Map-QUAK-DA22.pdf | QUAK-CA3-Map-QUAK-DA127.pdf | QUAK-CA3-Map-QUAK-DA128.pdf | QUAK-CA3-Map-QUAK-DA129.pdf
WA | ROCKINGHAM | RKHM | TBA | N/A | QRKHME4020M | NA | 6168 | 2014-04-30 | 2014-03-24 |  | RDLH-CA14-Area-Layout.pdf | RDLH-CA14-Map-RDLH-DA18.pdf | RDLH-CA14-Map-RDLH-DA14.pdf | RDLH-CA14-Map-RDLH-DA17.pdf
WA | ROCKINGHAM | RKHM | G47 | QRKHME3S3 | QBALDE4016M | DA47 | 6169 | 2014-01-31 | 2013-12-20
QLD | SAMFORD | SAOD | CA16 | QSAODE64M | QSAODE4007M | DA16 | 4520 | 2014-10-31 | 2014-09-30 |  | SAOD-CA16-Area-Layout.pdf | SAOD-CA16-Map-SAOD-DA16.pdf
VIC | SARSFIELD | SCAS | P509 | New | QSCASE4001M | DA500 | 3875 | 2014-01-31 | 2014-01-24
NSW | SEAHAM | SEAM | CA11 | QSEAME4001S2 | QSEAME4002M | DA11 | 2324 | 2014-11-30 | 2014-11-03 |  | SEAM-CA11-Area-Layout.pdf | SEAM-CA11-Map-SEAM-DA7.pdf | SEAM-CA11-Map-SEAM-DA9.pdf
VIC | SOMERTON | SRTN | CA15 | QSRTNE10S7 | QSRTNE4014M | DA85 | 3061 | 2014-06-30 | 2014-07-24
VIC | SOUTH MELBOURNE | SMEL | T109 |  | QSMELE4011M |  | 3006 | 2014-08-31 | 2014-08-31 | Y | [7 empty] | Eureka Towers
QLD | SPEEWAH | SPWH | CA1 | N/A | QSPWHE4002M | DA1 DA500 DA501 | 4881 | 2014-06-30 | 2014-06-16
VIC | SYDENHAM | SHAM | CA5 | QSHAME63M | QSHAME4024M | DA64; DA179 | 3037 | 2014-08-31 | 2014-07-21 |  | SHAM-CA5-Area-Layout.pdf | SHAM-CA5-Map-SHAM-DA64.pdf
NSW | TASHMOOR | TAMR | CA1 | QTAMRE4005M | QTAMRE4007M | DA1; DA19 | 2571 | 2014-11-30 | 2014-11-05 |  | TAMR-CA1-Area-Layout.pdf | TAMR-CA1-Map-TAMR-DA19.pdf | TAMR-CA1-Map-TAMR-DA1.pdf
QLD | TINGALPA | TGPA | CA79 | QTGPAE57M | QTGPAE4015M | DA79 | 4172 | 2014-08-31 | 2014-07-31 |  | TGPA-CA79-Area-Layout.pdf | TGPA-CA79-Map-TGPA-DA79.pdf
NSW | ULLADULLA | ULLA | CA6 | QULLAE4005M | QULLAE4015M | DA2; DA27 | 2539 | 2014-11-30 | 2014-09-26 |  | ULLA-CA6-Area-Layout.pdf | ULLA-CA6-Map-ULLA-DA27.pdf | ULLA-CA6-Map-ULLA-DA2.pdf
NSW | WALLSEND | WLSD | CA107 | QWLSDE4007M | QWLSDE4003M | DA107 | 2287 | 2015-04-30 | 2015-02-09
NSW | WOLLONGONG | WLGG | CA245 | QWLGGE4034M | QWLGGE4013M | DA107; DA159; DA160; DA162; DA164 | 2525 | 2014-11-30 | 2014-11-11 |  | WLGG-CA245-Area-Layout.pdf | WLGG-CA245-Map-WLGG-DA107.pdf | WLGG-CA245-Map-WLGG-DA164.pdf | WLGG-CA245-Map-WLGG-DA160.pdf | WLGG-CA245-Map-WLGG-DA159.pdf | WLGG-CA245-Map-WLGG-DA162.pdf
QLD | WULGURU | WLGU | G45 | QWLGUE4006M | TBA | DA46 | 4816 | 2014-05-31 | 2014-05-12
QLD | WURTULLA | WURT | G87 | QWURTE4007M | QWURTE4021M | DA85; DA86; DA87 | 4557 | 2014-08-31 | 2014-08-06 |  | WURT-G86-Area-Layout.pdf | WURT-G86-Map-WURT-DA85.pdf | WURT-G86-Map-WURT-DA86.pdf |  |  |  |  | WURT DA87 is a proposed DA
QLD | YANDARAN | YAND | G12 | NA | QYANDE4003 | DA3, DA10 | 4670 | 2014-12-31 | 2014-12-18
QLD | YEPPOON | YEPP | CA100 | QYEPPE31M | QYEPPE4009M | DA41; DA40; DA44; DA44; DA47 | 4703 | 2014-11-30 | 2014-11-14
QLD | YEPPOON | YEPP | CA100 | QYEPPE40M | QYEPPE4009M | DA41; DA40; DA44; DA44; DA47 | 4703 | 2014-11-30 | 2014-11-14
NSW | CAMPBELLTOWN | CBTN | CA2 | QCBTNE4010M | QCBTNE4041M | DA108 | 2560 | 2015-07-31 | 2015-05-22
QLD | COOLUM BEACH | CLMB | CA40 | QCLMBE21M | QCLMBE4012M | DA14; DA34 | 4573 | 2015-04-30 | 2015-02-13 | Y
NSW | MONA VALE | MONA | CA2 | QMONAE4005M | QMONAE4012M | DA310; DA311; DA312; DA313; DA314; DA315; DA316 | 2104 | 2015-07-31 | 2015-05-06
QLD | MOOLOOLABA | MOOH | CA84 | QMOOHE6M | QMOOHE4013M | DA84 | 4572 | 2015-04-30 | 2015-02-09 | Y
QLD | NARANGBA | NRBA | CA53 | QNRBAE59M | QNRBAE4007M | DA20; DA62 | 4505 | 2015-04-30 | 2015-03-05 | Y
NSW | NARELLAN | NRLN | CA52 | QNRLNE4022M | QNRLNE4052M | DA51; DA52 | 2557 | 2015-04-30 | 2015-03-06
WA | ARMADALE | ARMD | CA8 | QARMDE3M | QARMDE4011M | DA77 | 6112 | 2015-06-30 | 2015-06-01
WA | BALDIVIS | BALD | CA3 | QBALDE6M | QBALDE4018M | DA6; DA7 | 6171 | 2015-06-30 | 2015-06-12 | Y
VIC | BELMONT | BELM | G14 | QBELME6S7 | QBELME4007M | DA134 | 3216 | 2014-05-31 | 2014-05-26
WA | CANNINGTON | CANN | P139 | QCANNE30M | QCANNE4014M | DA139 | 6107 | 2015-06-30 | 2015-05-26 | Y
WA | COTTESLOE | CTOE | P36 | N/A | QCTOEE4003M | DA36 | 6010 | 2014-07-31 | 2014-07-31
QLD | EIMEO | EMEO | CA19 | QEMEOE16M | QEMEOE4005M | DA18 | 4740 | 2015-04-30 | 2015-03-19
QLD | EIGHT MILE PLAINS | EMPS | CA105 | N/A | QEMPSE4014M | DA105; DA94 | 4117 | 2014-06-30 | 2014-06-20
VIC | EPSOM | EPSO | CA3 | QEPSOE2M | QEPSOE4004M | DA5 | 3551 | 2015-07-31 | 2015-06-24
WA | GUILDERTON | GLDN | P4 | QGLDNE3M | QGLDNE4001M | DA4 | 6041 | 2015-06-30 | 2015-05-18
NSW | Helensburgh CA9 | HBGH | CA9 | QHBGHE4001S3 | QHBGHE4008M | DA9 | 2508 | 2015-07-31 | 2015-05-28
NT | HOWARD SPRINGS | HDSS | CA31 | QHDSSE19M | QHDSSE4008M | DA31; DA32; DA33; DA34; DA35; DA36; DA37 | 0839 | 2015-04-30 | 2014-12-03
NT | HOWARD SPRINGS | HDSS | P15 | QHDSSE3M | QHDSSE4007M | DA15 | 0839 | 2015-04-30 | 2014-12-03
VIC | KANGAROO FLAT | KGRO | CA1 | QKGROE4M | QKGROE4003M | DA33; DA39 | 3555 | 2015-07-31 | 2015-06-29
QLD | MAROOCHY RIVER | MARR | CA8 | QMARRE34M | QMARRE4001M | DA3; DA4 | 4560 | 2015-04-30 | 2015-02-03
QLD | NEWTOWN | NEWO | CA77 | QNEWOE96M | QNEWOE4010M | DA77 | 4350 | 2015-04-30 | 2015-01-27
VIC | ROCKBANK | RKBK | P11 |  | TBA | DA11 |  | 2015-05-31 | 2015-04-07
WA | SCARBOROUGH | SCBH | P69 | QSCBHE5M | QSCBHE4003 | DA69 | 6019 | 2015-07-31 | 2015-06-29 | Y
QLD | TAMBORINE | TBNE | CA9 | QTBNEE30M | QTBNEE4003M | DA3 | 4285 | 2015-04-30 | 2015-02-02
VIC | KARINGAL | KALG | CA64 | QKALGE2S4 | QKALGE4013M | DA56 | 3910 | 2014-09-30 | 2014-09-25
VIC | OCEAN GROVE | OCGR | CA1 | QOCGRE3M | QOCGRE4004M | DA9 | 3226 | 2015-03-31 | 2015-02-25
NSW | Miranda | MIRA | P198 |  | QMIRAE4020M | DA198 | 2228 | 2015-04-30 | 2015-04-30
NSW | LAVINGTON | LAVN | CA103 | QLAVNE4004M | QLAVNE4022M | DA103 | 2640 | 2015-07-31 | 2015-06-30
QLD | CALOUNDRA | CALO | CA54 | QCALOE5S6 | QCALOE4015M | DA53; DA123 | 4551 | 2015-06-30 | 2015-03-02
QLD | HIGHFIELDS | HFDS | CA23 | QHFDSE5S2 | QHFDSE4010M | DA17 | 4352 | 2015-06-30 | 2015-05-21
WA | CANNINGTON | CANN | BHUC01 | QCANNE82M | QCANNE4015M | DA1; DA3; DA125; DA126; DA128; DA129 | 6107 | 2015-03-31 | 2015-03-10 | Y
NSW | CASTLE HILL | CAST | CA15 | QCASTE4010M | QCASTE4031M | DA147; DA120; DA99 | 2154 | 2015-06-30 | 2015-05-22
QLD | Albany Creek | ABCK | CA66 | QABCKE33S2 | QABCKE4007M | DA18; DA39 | 4037 | 2015-02-28 | 2015-02-02 | Y
NSW | ALBURY | ALBY | CA133 | QALBYE4006M | QALBYE4026M | DA133 | 2640 | 2015-07-31 | 2015-07-09
NSW | ALBURY | ALBY | CA115 | QALBYE4010M | QALBYE4024M | DA115; DA77 | 2640 | 2015-07-31 | 2015-06-19 | Y
VIC | WODONGA | WDGA | CA49 | QWDGAE4003M | QWDGAE4002M | DA49 | 3689 | 2015-10-31 | 2015-10-16
NSW | ERINA | ERNA | CA3 | QERNAE4007M | QERNAE4002M | DA3 | 2250 | 2015-06-30 | 2015-06-04
NSW | GOULBURN | GLBN | CA125 | QGLBNE4011M | QGLBNE4025M | DA123; DA125; D126 | 2580 | 2015-07-31 | 2015-06-22 | Y
NSW | GOULBURN | GLBN | CA115 | QGLBNE4009M | QGLBNE4026M | DA115; DA103 | 2580 | 2015-07-31 | 2015-06-24 | Y
ACT | SCULLIN | SCLN | CA7 | QSCLNE4002M | QSCLNE4015M | DA77 | 2615 | 2015-07-31 | 2015-06-22
QLD | BOREEN POINT | BORE | CA3 | QBOREE12M | QBOREE4001M | DA6; DA500 | 4565 | 2015-05-31 | 2015-05-01
QLD | TRINITY | TRIN | CA37 | QTRINE43M | QTRINE4005M | DA35; DA37 | 4879 | 2015-05-31 | 2015-04-24 | Y
QLD | BUDERIM | BUDE | CA70 | QBUDEE12M | QBUDEE4015M | DA70 | 4556 | 2015-05-31 | 2015-04-28
QLD | CLINTON | CNON | CA100 | QCNONE40M | QCNONE4005M | DA28; DA36 | 4680 | 2015-05-31 | 2015-04-29
QLD | EMU PARK | EMPK | CA16 | QEMPKE5M | QEMPKE4003M | DA2; DA16 | 4703 | 2015-07-31 | 2015-06-15
QLD | EUMUNDI | EUMU | CA4 | QEUMUE8M | QEUMUE4004M | DA6 | 4562 | 2015-06-30 | 2015-04-07
QLD | MAROOCHY RIVER | MARR | CA7 | QMARRE35M | QMARRE4002M | DA1; DA5; DA6 | 4561 | 2015-06-30 | 2015-05-21
QLD | MUDJIMBA | MUDJ | CA13 | QMUDJE13M | QMUDJE4011M | DA13 | 4564 | 2015-06-30 | 2015-04-02
QLD | NOOSAVILLE | NOOV | CA58 | QNOOVE30M | QNOOVE4005M | DA30; DA51 | 4565 | 2015-06-30 | 2015-06-11
NSW | LAMMERMOOR | LAMM | CA110 | QLAMME8S2 | QLAMME4002M | DA105; DA109 | 4703 | 2015-06-30 | 2015-06-05
VIC | SOMERTON | SRTN | CA14 | QSRTNE10S6 | QSRTNE4011M | DA84; DA86 | 3062 | 2015-09-30 | 2015-08-31
NSW | NARARA | NAAA | G2 | QNAAAE4012M |  | G2 |  | 2015-04-30 | 2015-03-19
QLD | ROMA | ROMA | G40 |  | QROMAE4005M | DA40 | 4455 | 2015-07-31 | 2015-07-09
NSW | OURIMBAH | OBAH | CA17 | QOBAHE4005M | QOBAHE4006M | DA17 | 2250 | 2015-07-31 | 2015-06-30
NSW | TERRIGAL | TRGL | CA1 | QTRGLE4003M | QTRGLE4016M | DA1 | 2261 | 2015-09-30 | 2015-07-03
QLD | BURLEIGH HEADS | BURL | CA5 | QBURLE17M | QBURLE4009M | DA113; DA114 | 4220 | 2015-05-31 | 2015-04-23 | Y
QLD | INNISFAIL | INNI | CA1 | QINNIE61M | QINNIE4003M | DA11; DA12; DA21; DA40 | 4860 | 2015-10-31 | 2015-10-23
QLD | STEPHENS | SPHS | CA24 | QSPHSE19M | QSPHSE4007M | DA24; DA26 | 4227 | 2015-06-30 | 2015-05-28 | Y
WA | MADDINGTON | MADD | P80 | QMADDE4M | QMADDE4010M | DA80 | 6109 | 2015-05-31 | 2015-05-12
NSW | ORANGE | ORGF | CA123 |  | QORGFE4017M | DA122; DA123; DA132 | 2800 | 2015-05-31 | 2015-04-17 | Y
QLD | BORALLON | BORA | CA4 |  | QBORAE4001M | DA500 | 4306 | 2015-04-30 | 2015-03-19
NSW | PYMBLE | PYMB | CA17 | QPYMBE10S2 | QPYMBE4003M | DA206; DA203 | 2073 | 2016-01-31 | 2015-12-11
NSW | KELLYVILLE | KELL | CA7 | QKELLE4035M | QKELLE4015M | DA8; DA10; DA27 | 2768 | 2015-11-30 | 2015-10-27 | Y
NSW | WINMALEE | WNML | CA1 | QWNMLE4004M | QWNMLE4006M | DA23; DA25 | 2777 | 2015-09-30 | 2015-09-08 | Y
NSW | TERREY HILLS | TERR | CA3 | QTERRE20S2 | QTERRE4006M | DA1; DA7 | 2084 | 2016-06-30 | 2016-07-27 | Y
SA | MOUNT GAMBIER | MTGE | CA15 | QMTGEE14M | QMTGEE4013M | DA125 | 5290 | 2015-10-31 | 2015-10-22 | Y
NSW | BRAXTON | BRXN | CA8 | QBRXNE4002M | QBRXNE4004M | DA8; DA17 | 2335 | 2015-12-31 | 2015-11-03 | Y
NSW | MURWILLUMBAH | MBAH | CA5 | QMBAHE4003M | QMBAHE4002M | DA5 | 2484 | 2015-12-31 | 2015-11-06
NSW | TARRO | TARR | CA31 | QTARRE4008M | QTARRE4005M | DA31; DA54 | 2322 | 2015-12-31 | 2015-12-10 | Y
QLD | BLUEWATER | BLUE | CA1 | QBLUEE4M | QBLUEE4002M | DA6; DA11 | 4818 | 2015-10-31 | 2015-10-15 | Y
NSW | MOUNT HUTTON | MTHN | CA10 | QMTHNE4003M | QMTHNE4011M | DA10 | 2282 | 2015-12-31 | 2015-12-03 | Y
NSW | MAITLAND | MAIT | CA124 | QMAITE4013M | QMAITE4012M | DA124 | 2323 | 2015-12-31 | 2015-11-11 | Y
VIC | DEER PARK | DRPK | CA17 | QDRPKE23M | QDRPKE4024M | DA114; DA115 | 3023 | 2016-02-29 | 2016-02-08 | Y
VIC | DEER PARK | DRPK | CA10 | QDRPKE5M | QDRPKE4023M | DA99 | 3023 | 2015-12-31 | 2015-12-14 | Y
QLD | FRESHWATER | FRES | CA2 | QFRESE25M | QFRESE4003M | DA17; DA20 | 4878 | 2015-10-31 | 2015-10-21 | Y
QLD | MOUNT ISA | MTIF | CA8 | QMTIFE67M | QMTIFE4013M | DA56; DA57; DA80 | 4825 | 2015-10-31 | 2015-10-06 | Y
QLD | MOUNT ISA | MTIF | CA5 | QMTIFE64M | QMTIFE4014M | DA33 | 4825 | 2015-10-31 | 2015-09-30 | Y
QLD | NINGI | NING | CA4 | QNINGE7M | QNINGE4003M | DA4; DA10 | 4511 | 2015-10-31 | 2015-10-06 | Y
QLD | SLADE POINT | SLAD | CA33 | QSLADE25M | QSLADE4009M | DA33 | 4740 | 2015-10-31 | 2015-10-08
QLD | EVERTON PARK | ENPK | CA32 | QENPKE36M | QENPKE4004M | DA32 | 4035 | 2015-10-31 | 2015-10-07
QLD | CALOUNDRA | CALO | CA37 | QCALOE19M | QCALOE4016M | DA67; DA70 | 4551 | 2015-10-31 | 2015-10-16 | Y
NSW | CASTLE HILL | CAST | CA1 | QCASTE4016M | QCASTE4001M | DA99; DA152; DA154 | 2126 | 2015-10-31 | 2015-10-08 | Y
QLD | ORMEAU | ORME | CA56 | QORMEE36S3 | QORMEE4009M | DA40; DA57; DA58 | 4209 | 2015-10-31 | 2015-09-23
NSW | WILTON | WILT | CA1 | QWILTE4003M | QWILTE4004M | DA1 | 2571 | 2015-12-31 | 2015-12-15 | Y
QLD | MORAYFIELD | MRFD | CA36 | QMRFDE19M | QMRFDE4008M | DA36 | 4505 | 2015-10-31 | 2015-09-18
QLD | MUDGEERABA | MGBA | CA34 | QMGBAE73M | QMGBAE4007M | DA34 | 4213 | 2015-10-31 | 2015-09-30
QLD | IPSWICH | IPSW | CA87 | QIPSWE30M | QIPSWE4008M | DA87 | 4306 | 2015-10-31 | 2015-10-06
QLD | MOUNT COTTON | MTCN | CA3 | QMTCNE25M | QMTCNE4003M | DA9 | 4165 | 2015-10-31 | 2015-10-06
QLD | MORAYFIELD | MRFD | CA17 | QMRFDE16M | QMRFDE4007M | DA38; DA17; DA24 | 4506 | 2015-10-31 | 2015-10-01
QLD | ARUNDEL | ARUN | CA2 | QARUNE25M | QARUNE4014M | DA46 | 4214 | 2015-10-31 | 2015-10-07 | Y
QLD | CABOOLTURE | CABO | CA70 | QCABOE8M | QCABOE4017M | DA70; DA136; DA31 | 4510 | 2015-10-31 | 2015-09-22 | Y
NSW | NORDS WHARF | NRDS | CA16 | QNRDSE4006M | QNRDSE4014M | DA8; DA10 | 2259 | 2015-12-31 | 2015-12-11 | Y
NSW | NORDS WHARF | NRDS | CA1 | QNRDSE4007M | QNRDSE4015M | DA13; DA14; DA11; DA12 | 2259 | 2015-12-31 | 2015-11-18 | Y
NSW | TORONTO | TRTO | CA64 | QTRTOE4006M | QTRTOE4021M | DA64 | 2284 | 2015-12-31 | 2015-12-10
NSW | MORISSET | MRSE | CA18 | QMRSEE4005M | QMRSEE4019M | DA18; DA32 | 2264 | 2015-12-31 | 2015-11-23 | Y
NSW | BATEMANS BAY | BATE | CA21 | QBATEE4005M | QBATEE4020M | DA47; DA48 | 2536 | 2016-01-31 | 2015-12-22
NSW | MEDOWIE | MDWI | CA19 | QMDWIE4004M | QMDWIE4009M | DA19; DA24 | 2318 | 2015-12-31 | 2015-12-11
NSW | TUMUT | TUMU | CA32 | QTUMUE4004M | QTUMUE4008M | DA32 | 2720 | 2016-01-31 | 2015-12-18
NSW | SINGLETON | SING | CA77 | QSINGE4001S4 | QSINGE4010M | DA76; DA78 | 2330 | 2015-12-31 | 2015-12-11
NSW | GOULBURN | GLBN | CA108 | QGLBNE4014M | QGLBNE4027M | DA109; DA112 | 2580 | 2015-12-31 | 2015-12-08 | Y
QLD | CAPALABA | CPBA | CA2 | QCPBAE53M | QCPBAE4005M | DA33; DA34 | 4157 | 2015-12-31 | 2015-11-04
QLD | JIMBOOMBA | JBBB | CA3 | QJBBBE54M | QJBBBE4012M | DA16 | 4280 | 2015-12-31 | 2015-11-18
QLD | JIMBOOMBA | JBBB | CA4 | QJBBBE53M | QJBBBE4011M | DA22 | 4280 | 2015-12-31 | 2015-11-05
QLD | JIMBOOMBA | JBBB | CA23 | QJBBBE4S2 | QJBBBE4010M | DA32; DA33 | 4280 | 2015-12-31 | 2015-10-28
WA | MUNDARING | MDNG | CA3 | QMDNGE4002M | QMDNGE4002M | DA7; DA13 | 6073 | 2016-01-31 | 2015-11-05 | Y
VIC | OCEAN GROVE | OCGR | CA4 | QOCGRE1S2 | QOCGRE4007M | DA37; DA38 | 3226 | 2015-12-31 | 2015-12-11
WA | GELORUP | GLRP | CA4 | QGLRPE48M | QGLRPE4014M | DA2; DA5 | 6230 | 2016-01-31 | 2016-01-08
WA | BYFORD | BYFD | P7 | QBYFDE5M | QBYFDE4011M | DA77 | 6122 | 2016-01-31 | 2015-10-21
WA | WANNEROO | WANO | P74 | QWANOE157M | QWANOE4020M | DA74 | 6065 | 2016-01-31 | 2015-11-02
NSW | POKOLBIN | POKO | CA9 | QPOKOE4001S3 | QPOKOE4007M | DA9 | 2320 | 2015-12-31 | 2015-12-11
VIC | IRYMPLE | IRYM | CA1 | QIRYME2M | QIRYME4002M | DA18; DA20 | 3498 | 2015-12-31 | 2015-12-09
WA | WUNDOWIE | WUND | G6 |  | QWUNDE4001M | DA6 | 6560 | 2016-05-20 | 2016-01-31
VIC | GISBORNE | GISB | CA2 | QGISBE92M | QGISBE4004M | DA21 | 3438 | 2016-05-31 | 2016-04-30
NSW | BATHURST | BATH | CA76 | QBATHE4017M | QBATHE4049M | DA109 | 2795 | 2015-12-31 | 2016-04-30
QLD | ALBANY CREEK | ABCK | CA67 | QABCKE33S3 | QABCKE4008M | DA62; DA68 | 4037 | 2015-12-31 | 2015-12-31
WA | KARRATHA | KAHA | G54 |  | QKAHAE4006M | DA54 | 6714 | 2017-01-31 | 2016-03-31
WA | LANDSDALE | LDLE | G49 |  | QLDLEE4005M | DA49 | 6065 | 2015-07-31 | 2015-07-30
NSW | REGENTVILLE | REVL | CA1 | QREVLE4005M | QREVLE4016M | DA72;DA82 | 2745 | 2016-04-30 | 2016-04-30 | Y
NSW | KURRAJONG HEIGHTS | KRJH | CA1 | QKRJHE4002M | QKRJHE4004M | DA11 | 2758 | 2016-05-31 | 2015-12-31
NSW | NARELLAN | NRLN | CA72 | QNRLNE4021M | QNRLNE4054M | DA72 | 2567 | 2016-04-30 | 2015-12-31 | Y
NSW | EDENSOR PARK | ERPK | CA7 | QERPKE4005M | QERPKE4019M | DA7;DA17 | 2177 | 2016-06-24 | 2015-11-30 | Y
NSW | HASTINGS POINT | HASP | CA15 | QHASPE4008M | QHASPE4020M | DA15 | 2489 | 2016-04-30 | 2016-03-31
QLD | WOOROOLIN | WLIN | G1 |  | QWLINE4002M | DA1 | 4610 | 2016-01-29 | 2015-12-31
WA | LANDSDALE | LDLE | G59 | QLDLEE2S6 | QLDLEE4014M | DA49 | 6065 | 2015-07-31 | 2015-12-31
QLD | MOLLOY | MOLL | CA3 | QMOLLE25S2 | QMOLLE4002M | DA3;DA5 | 4871 | 2015-12-31 | 2016-02-29
NSW | MOREE | MREE | CA53 | QMREEE4004M | QMREEE4010M | DA53 | 2400 | 2016-03-31 | 2015-11-30
ACT | MELBA | MLBA | CA78 | QMLBAE4011M | QMLBAE4020M | DA78 | 2615 | 2016-04-30 | 2015-12-31
NSW | TWEED HEADS WEST | TDHW | CA9 | QTDHWE4002M | QTDHWE4007M | DA9; DA12 | 2485 | 2016-04-30 | 2015-11-30
NSW | NARARA | NAAA | CA44 | QNAAAE4006M | QNAAAE4014M | DA44; DA3 | 2250 | 2016-03-31 | 2016-01-31 | Y
NSW | WEST TAMWORTH | WTAM | CA28 | QWTAME4003M | QWTAME4027M | DA28 | 2340 | 2016-05-31 | 2016-03-31
QLD | KALLANGUR | KLGR | CA40 | QKLGRE51M | QKLGRE4033M | DA40 | 4503 | 2015-12-31 | 2015-12-31
SA | PORT WAKEFIELD | PWAK | P5 |  | QPWAKE4002M | DA500 | 5550 | 2015-09-30 | 2015-09-03
QLD | ARUNDEL | ARUN | CA49 | QARUNE26M | QARUNE4015M | DA49; DA67 | 4214 | 2015-12-31 | 2016-01-31
QLD | KALLANGUR | KLGR | G154 |  | QKLGRE4032M | DA154 | 4509 | 2015-12-31 | 2016-07-31
QLD | PEREGIAN BEACH | PRGN | CA19 | QPRGNE4S4 | QPRGNE4006M | DA18; DA21 | 4573 | 2016-02-29 | 2016-04-30
QLD | MORAYFIELD | MRFD | CA34 | QMRFDE17M | QMRFDE4010M | DA34 | 4505 | 2016-01-31 | 2016-02-29
QLD | ORMEAU | ORME | CA8 | QORMEE39M | QORMEE4024M | DA8 | 4208 | 2016-01-31 | 2015-12-31
QLD | MORAYFIELD | MRFD | CA24 | QMRFDE18M | QMRFDE4009 | DA24 | 4506 | 2016-01-31 | 2015-12-31 | Y
NSW | GRIFFITH | GFTH | CA105 | QGFTHE4001S7 | QGFTHE4022M | DA105;DA107;DA108 | 2680 | 2016-05-31 | 2016-04-30
NSW | KELLYVILLE | KELL | CA1 | QKELLE4034M | QKELLE4034M | DA1;DA2 | 2768 | 2016-04-30 | 2016-03-31 | Y
QLD | VERESDALE | VERE | CA5 | QVEREE10M | QVEREE10M | DA5 | 4285 | 2015-12-31 | 2016-03-03
VIC | BAXTER | BAXR | P24 |  | QBAXRE4002M | DA24 | 3911 | 2016-05-31 | 2016-04-30 |  | https://www.telstrawholesale.com.au/content/dam/tw/maps/vic/baxr/p24/BAXR-P24-Area-Layout.pdf | https://www.telstrawholesale.com.au/content/dam/tw/maps/vic/baxr/p24/BAXR-P24-Map-BAXR-DA24.pdf
NSW | MIRANDA | MIRA | CA5 | QMIRAE4003M | QMIRAE4022M | DA57;DA140;DA164;DA162;DA34;DA85;DA196 | 2232 | 2016-06-30 | 2016-03-31 | Y
ACT | BELCONNEN | BLCN | CA67 | QBLCNE4002M | QBLCNE4015M | DA19 | 2617 | 2016-04-30 | 2016-03-31
QLD | FERNY HILLS | FHLS | G86 |  | QFHLSE4012M | DA87 | 4055 | 2016-03-31 | 2016-03-31
NSW | CARDIFF | CRDF | CA70 | QCRDFE4007M | QCRDFE4026 | DA20; DA59; DA46; DA70 | 2285 | 2016-05-31 | 2016-03-31
VIC | DEER PARK | DRPK | G68 |  | QDRPKE4025M | DA68; DA69 | 3023 | 2016-07-29 | 2016-01-31 | Y
NSW | KELLYVILLE | KELL | CA18 | QKELLE4037M | QKELLE4071M | DA304;DA413 | 2155 | 2016-07-31 | 2016-05-31 | Y
NSW | COBBITTY | CBTY | CA6 | QCBTYE4002M | QCBTYE4004M | DA6 | 2570 | 2016-08-31 | 2016-07-31
QLD | PALMWOODS | PMWS | CA15 | QPMWSE26M | QPMWSE4006M | DA1; DA15 | 4554 | 2016-04-30 | 2016-04-30
NSW | ROOTY HILL | ROOT | CA3 | QROOTE4002M | QROOTE4012M | DA243;DA239;DA401 | 2770 | 2016-09-16 | 2016-03-31 | Y
NSW | NARRABEEN | NARR | CA1 | QNARRE4005M | QNARRE4008M | DA21;DA22;DA23 | 2101 | 2016-06-10 | 2016-07-31 | Y
QLD | MUDGEERABA | MGBA | CA26 | QMGBAE80M | QMGBAE4024M | DA8; DA26 | 4213 | 2016-04-30 | 2016-05-31
QLD | TINGALPA | TGPA | CA61 | QTGPAE59M | QTGPAE4016M | DA61; DA6 | 4174 | 2016-04-30 | 2016-05-31 | Y
NSW | ORCHARD HILLS | ORHS | CA43 | QORHSE4003M | QORHSE4010 | DA42;DA43 | 2748 | 2016-02-29 | 2016-07-31 | Y
QLD | CALOUNDRA | CALO | CA100 | QCALOE23M | QCALOE4022M | DA100; DA110 | 4551 | 2016-04-30 | 2016-02-29
NSW | BILPIN | BLPN | CA1 | QBLPNE4003M | QBLPNE4005M | DA1 | 2758 | 2016-06-10 | 2016-07-31
NSW | RAZORBACK | RZBK | CA8 | QRZBKE4004M | QRZBKE4005M | DA8 | 2571 | 2016-06-30 | 2016-06-30
VIC | RED CLIFFS | REFS | CA6 | QREFSE5M | QREFSE4003M | DA28 | 3496 | 2016-06-24 | 2016-06-30
VIC | RED CLIFFS | REFS | CA6 | QREFSE5M | QREFSE4002M | DA28 | 3496 | 2016-06-24 | 2016-06-30
VIC | MORWELL | MWRL | CA14 | QMWRLE65M | QMWRLE4006M | DA80 | 3840 | 2016-09-30 | 2016-06-30
VIC | MORWELL | MWRL | CA14 | QMWRLE65M | QMWRLE4005M | DA80 | 3840 | 2016-09-30 | 2016-06-30
VIC | SEBASTOPOL | SPOL | CA2 | QSPOLE26M | QSPOLE4005M | DA39 | 3356 | 2016-09-30 | 2017-08-31
VIC | SEBASTOPOL | SPOL | CA2 | QSPOLE26M | QSPOLE4004M | DA39 | 3356 | 2016-09-30 | 2017-08-31
QLD | BUDERIM | BUDE | CA84 | QBUDEE8M | QBUDEE4018M | DA83; DA86 | 4556 | 2016-07-31 | 2017-08-31 | Y
QLD | LOGAN VILLAGE | LOGA | G25 |  | QLOGAE4004M | DA14; DA26 | 4207 | 2016-04-29 | 2016-04-21
NSW | LLANDILO | LLDO | CA1 | QLLDOE4015M | QLLDOE4016 | DA3;DA10 | 2749 | 2016-06-10 | 2016-05-31
NSW | NARELLAN | NRLN | CA57 | QNRLNE4003M | QNRLNE4055 | DA57 | 2567 | 2016-06-10 | 2016-05-12
NSW | BATEMANS BAY | BATE | CA30 | QBATEE4007M | QBATEE4022M | DA14; DA30 | 2536 | 2016-07-31 | 2016-07-28
NSW | LISMORE | LISM | CA9 | QLISME4003M | QLISME4013M | DA9; DA34 | 2480 | 2016-06-30 | 2016-05-11
NSW | KEMPSEY | KMSY | CA52 | QKMSYE4003M | QKMSYE4013M | DA52 | 2440 | 2016-06-30 | 2016-04-19
WA | RIVERTON | RIVT | P49 | QRIVTE24M | QRIVTE4005M | DA49 | 6148 | 2016-06-30 | 2016-05-31 | Y
WA | GIDGEGANNUP | GGNP | P7 | QGGNPE7M | QGGNPE4002M | DA7 | 6083 | 2016-06-30 | 2016-05-24
WA | FORRESTDALE | FTDL | P22 | QFTDLE3M | QFTDLE4008M | DA22 | 6121 | 2016-06-30 | 2016-06-03
WA | GREENMOUNT | GRMT | P21 | QGRMTE10M | QGRMTE4002M | DA21 | 6056 | 2016-06-30 | 2016-05-24 | Y
VIC | TARNEIT | TNIT | CA2 | QTNITE9M | QTNITE4031M | DA80; DA86 | 3029 | 2016-06-30 | 2016-06-23 | Y
VIC | LYNDHURST | LYNH | CA14 | QLYNHE6S7 | QLYNHE4009M | DA81; DA89 | 3975 | 2016-06-30 | 2016-06-23
VIC | LYNDHURST | LYNH | CA9 | QLYNHE6S2 | QLYNHE4008M | DA68 | 3975 | 2016-06-30 | 2016-06-23
NSW | ORCHARD HILLS | ORHS | CA5 |  | QORHSE4011M | DA43 | 2748 | 2016-06-10 | 2016-06-01 | Y | ORHS-CA5-Area-Layout.pdf | ORHS-CA5-Map-ORHS-DA43.pdf
VIC | LEOPOLD | LEOP | CA3 | QLEOPE36M | QLEOPE4005M | DA519; DA500 | 3221 | 2016-04-29 | 2016-04-13
VIC | COLDSTREAM | COLD | CA2 |  | QCOLDE4002M | DA6 | 3770 | 2016-03-11 | 2015-12-22
QLD | GREENBANK | GRBK | CA15 | QGRBKE18M | QGRBKE4004M | DA15 | 4124 | 2016-06-30 | 2016-05-20
QLD | STEPHENS | SPHS | CA31 | QSPHSE16M | QSPHSE4008M | DA31 | 4227 | 2016-06-30 | 2016-05-22
VIC | DEER PARK | DRPK | CA30 | QDRPKE45M | QDRPKE4026M | DA145; DA147 | 3023 | 2016-06-30 | 2016-05-31 | Y
VIC | DEER PARK | DRPK | CA25 | QDRPKE15M | QDRPKE4027M | DA131; DA125 | 3023 | 2016-06-30 | 2016-05-31 | Y
NSW | LIVERPOOL | LIVE | CA242 | QLIVEE4S4 | QLIVEE4025M | DA610;DA612 | 2170 | 2016-09-14 | 2016-07-31
NSW | HORSLEY PARK | HORS | CA1 | QHORSE4003S2 | QHORSE4005M | DA13;DA14;DA16 | 2766 | 2016-09-21 | 2016-07-31
NSW | ERSKINE PARK | ESPK | CA90 | QESPKE1S3 | QESPKE4008M | DA90 | 2759 | 2016-08-31 | 2016-07-31
NSW | REVESBY | REVE | CA22 | QREVEE5S3 | QREVEE4015M | DA117; DA158 | 2212 | 2016-09-21 | 2016-04-30 | Y
NSW | WARRAGAMBA | WGBA | CA2 | QWGBAE4003S2 | QWGBAE4007M | DA20 | 2745 | 2016-09-21 | 2016-02-29
WA | GUILDERTON | GLDN | CA3 | QGLDNE2M | QGLDNE4002M | DA5 | 6041 | 2016-06-30 | 2016-07-31
WA | WANNEROO | WANO | P65 | QWANOE156M | QWANOE4022M | DA65 | 6065 | 2016-04-30 | 2016-06-30
WA | WANNEROO | WANO | P65 | QWANOE156M | QWANOE4021M | DA65 | 6065 | 2016-04-30 | 2016-06-30
WA | NARROGIN | NRGN | CA20 | QNRGNE9M | QNRGNE4003M | DA20 | 6312 | 2016-07-31 | 2016-06-30
WA | HERNE HILL | HERL | P19 | QHERLE12M | QHERLE4004M | DA19 | 6056 | 2016-12-31 | 2016-06-30 | Y
WA | HERNE HILL | HERL | P19 | QHERLE12M | QHERLE4003M | DA19 | 6056 | 2016-12-31 | 2016-06-30 | Y
WA | SERPENTINE | SETI | P6 | QSETIE9M | QSETIE4002M | DA500 | 6125 | 2016-07-31 | 2016-06-30 | Y
WA | HAMERSLEY | HAMS | CA11 | QHAMSE360M | QHAMSE4021M | DA65;DA132 | 6022 | 2016-07-31 | 2016-06-30
WA | SCARBOROUGH | SCBH | P70 | QSCBHE3M | QSCBHE4005M | DA70 | 6019 | 2016-12-31 | 2017-08-31 | Y
NSW | BATEMANS BAY | BATE | CA5 | QBATEE4006M | QBATEE4021M | DA6; DA7; DA8; DA25; DA33 | 2536 | 2016-09-07 | 2016-08-25
WA | SCARBOROUGH | SCBH | P70 | QSCBHE3M | QSCBHE4004M | DA70 | 6019 | 2016-12-31 | 2017-08-31 | Y
ACT | MANUKA | MNKA | CA52 | QMNKAE4002M | QMNKAE4013M | DA50 | 2603 | 2016-08-31 | 2016-08-17
NSW | WEST TAMWORTH | WTAM | CA85 | QWTAME4007M | QWTAME4029M | DA85 | 2340 | 2016-08-31 | 2016-08-10
NSW | WEST TAMWORTH | WTAM | CA85 | QWTAME4007M | QWTAME4028M | DA85 | 2340 | 2016-08-31 | 2016-08-10
NSW | DUDLEY | DDLY | CA22 | QDDLYE4004M | QDDLYE4010M | DA22; DA7 | 2290 | 2016-06-30 | 2016-07-31
NSW | DUDLEY | DDLY | CA22 | QDDLYE4004M | QDDLYE4011M | DA7; DA22 | 2290 | 2016-06-30 | 2016-07-31
NSW | TORONTO | TRTO | CA27 | QTRTOE4011M | QTRTOE4022M | DA27; DA25 | 2283 | 2016-09-16 | 2016-07-31
NSW | TORONTO | TRTO | CA27 | QTRTOE4011M | QTRTOE4023M | DA25; DA27 | 2283 | 2016-09-16 | 2016-04-30
NSW | HASTINGS POINT | HASP | CA13 | QHASPE4011M | QHASPE4022M | DA13 | 2489 | 2016-09-21 | 2016-02-29
NSW | HASTINGS POINT | HASP | CA13 | QHASPE4011M | QHASPE4021M | DA13 | 2489 | 2016-09-21 | 2016-02-29
WA | HAMERSLEY | HAMS | CA11 | QHAMSE360M | QHAMSE4020M | DA65;DA132 | 6022 | 2016-07-31 | 2016-06-30
VIC | BELMONT | BELM | CA5 | QBELME101M | QBELME4010M | DA26 | 3216 | 2016-06-30 | 2016-06-30
VIC | LAVERTON | LTVN | CA35 | QLTVNE80S4 | QLTVNE4022M | DA138 | 3941 | 2016-09-07 | 2016-06-30 | Y
VIC | RYE | RYEE | CA12 | QRYEEE6S3 | QRYEEE4007M | DA4 | 3941 | 2016-09-07 | 2016-06-30
VIC | CHELSEA | CSEA | CA24 | QCSEAE101M | QCSEAE4009M | DA5;DA94 | 3197 | 2016-09-30 | 2016-09-30 | Y
VIC | BROOKLYN | BKLN | CA21 | QBKLNE16S5 | QBKLNE4003M | DA161 | 3026 | 2016-08-26 | 2016-08-18
VIC | WOODEND | WDND | P501 | QWDNDE13M | QWDNDE4006M | DA500 | 3442 | 2016-08-31 | 2016-08-04
VIC | WOODEND | WDND | P501 | QWDNDE13M | QWDNDE4005M | DA500 | 3442 | 2016-08-31 | 2016-08-04
NSW | HALLIDAYS POINT | HALP | CA10 | QHALPE4002M | QHALPE4007M | DA2; DA10; DA15 | 2430 | 2016-09-16 | 2016-08-03
NSW | HALLIDAYS POINT | HALP | CA10 | QHALPE4002M | QHALPE4006M | DA2; DA10; DA15 | 2430 | 2016-09-16 | 2016-08-03
NSW | NORDS WHARF | NRDS | CA19 | QNRDSE4005M | QNRDSE4017M | DA23 | 2281 | 2016-09-16 | 2016-07-26
NSW | NORDS WHARF | NRDS | CA19 | QNRDSE4005M | QNRDS E4018M | DA23 | 2281 | 2016-09-16 | 2016-07-26
VIC | LAVERTON | LTVN | CA16 | QLTVNE3M | QLTVNE4025M | DA104 | 3029 | 2016-09-21 | 2016-08-26 | Y
ACT | CRACE | CRCF | T3476 |  | QCRCFE4091M | DA85 | 2911 | 2016-07-31 | 2016-02-29
WA | JANDAKOT SOUTH | JTSX | CA14 | QJTSXE3S6 | QJTSXE4020M | DA74 | 6164 | 2016-10-31 | 2016-07-31
WA | JANDAKOT SOUTH | JTSX | CA14 | QJTSXE3S6 | QJTSXE4019M | DA74 | 6164 | 2016-10-31 | 2016-07-31
WA | ESPERANCE | ESPR | CA4 | QESPRE25S2 | QESPRE4011M | DA33 | 6450 | 2016-10-31 | 2016-06-30
WA | ESPERANCE | ESPR | CA4 | QESPRE25S2 | QESPRE4010M | DA33 | 6450 | 2016-10-31 | 2016-06-30
WA | DUNSBOROUGH | DBGH | CA6 | QDBGHE9S6 | QDBGHE4009M | DA30 | 6281 | 2016-10-31 | 2016-07-31
WA | DUNSBOROUGH | DBGH | CA6 | QDBGHE9S6 | QDBGHE4008M | DA30 | 6281 | 2016-10-31 | 2016-07-31
SA | HAMPSTEAD | HPSD | P146 |  | QHPSDE4009M | DA146 | 5086 | 2016-06-30 | 2016-04-30 | Y | HPSD-P146-Area-Layout. | HPSD-P146-Map-HPSD-P146
VIC | WODONGA | WDGA | CA108 | QWDGAE4001S6 | QWDGAE4024M | DA108 | 3690 | 2016-07-31 | 2016-06-29 | Y
QLD | REDLYNCH | RDLH | CA26 | QRDLHE24M | QRDLHE4008M | DA7; DA26 | 4780 | 2016-07-31 | 2016-05-25 | Y
QLD | MAROOCHYDORE | MYDE | CA74 | QMYDEE24M | QMYDEE4009M | DA17; DA54; DA70; DA74 | 4572 | 2016-07-31 | 2016-06-15 | Y
QLD | MAROOCHYDORE | MYDE | CA74 | QMYDEE24M | QMYDEE4008M | DA17; DA54; DA70; DA74 | 4572 | 2016-07-31 | 2016-06-15 | Y
QLD | BUDERIM | BUDE | CA82 | QBUDEE16M | QBUDEE4021M | DA82 | 4556 | 2016-07-31 | 2016-06-14
QLD | MARYBOROUGH | MBOR | CA111 | QMBORE82M | QMBORE4019M | DA88; DA103 | 4650 | 2016-08-31 | 2016-08-02 | Y
QLD | MARYBOROUGH | MBOR | CA111 | QMBORE82M | QMBORE4018M | DA88; DA103 | 4650 | 2016-08-31 | 2016-08-02 | Y
QLD | MUDJIMBA | MUDJ | CA20 | QMUDJE10M | QMUDJE4013M | DA20; DA25 | 4564 | 2016-09-07 | 2016-08-19 | Y
QLD | MUDJIMBA | MUDJ | CA20 | QMUDJE10M | QMUDJE4014M | DA20; DA25 | 4564 | 2016-09-07 | 2016-08-19 | Y
QLD | MOOLOOLABA | MOOH | CA69 | QMOOHE11M | QMOOHE4016M | DA33; DA67; DA69 | 4556 | 2016-07-31 | 2016-05-30 | Y
QLD | BUDERIM | BUDE | CA75 | QBUDEE7M | QBUDEE4020M | DA79; DA113 | 4556 | 2016-07-31 | 2016-05-25 | Y
NSW | SINGLETON | SING | CA74 | QSINGE4001S2 | QSINGE4011M | DA74; DA42 | 2330 | 2016-06-30 | 2016-02-29
VIC | DEER PARK | DRPK | G36 |  | QDRPKE4022M | DA184, DA185 | 3023 | 2016-02-29 | 2016-07-31
NSW | KARIONG | KRIG | CA3 | QKRIGE4003M | QKRIGE4008M | DA3; DA8; DA25 | 2250 | 2016-08-31 | 2016-06-30
NSW | TARRO | TARR | CA62 | QTARRE4001S6 | QTARRE4024M | DA62 | 2322 | 2016-08-31 | 2016-06-30
NSW | CARDIFF | CRDF | CA1 | QCRDFE4009M | QCRDFE4027M | DA1; DA36; DA37 | 2285 | 2016-09-30 | 2016-06-30
NSW | GRIFFITH | GFTH | CA99 | QGFTHE4001S2 | QGFTHE4023M | DA99 | 2680 | 2016-09-30 | 2016-09-19
NSW | NAROOMA | NRMA | CA13 | QNRMAE4006M | QNRMAE4010M | DA13 | 2546 | 2016-09-30 | 2016-09-09
NSW | NAROOMA | NRMA | CA13 | QNRMAE4006M | QNRMAE4009M | DA13 | 2546 | 2016-09-30 | 2016-09-09
NSW | KARIONG | KRIG | CA3 | QKRIGE4003M | QKRIGE4007M | DA3; DA8; DA25 | 2250 | 2016-08-31 | 2016-06-30
NSW | MOREE | MREE | CA67 | QMREE4001S3 | QMREEE4011M | DA67 | 2400 | 2017-06-30 | 2016-06-30
NSW | MOREE | MREE | CA67 | QMREE4001S3 | QMREEE4012M | DA67 | 2400 | 2017-06-30 | 2016-06-30
QLD | KARUMBA | KARU | CA1 | QKARUE5M | QKARUE4002M | DA500 | 4891 | 2016-10-31 | 2016-07-19
QLD | SEAFORTH | SFTH | CA1 | QSFTHE2M | QSFTHE4002M | DA1; DA5; DA6 | 4741 | 2016-05-31 | 2016-04-20 | Y
VIC | MORNINGTON | MORN | CA33 | QMORNE5S7 | QMORNE4013M | DA92, DA97, DA100 | 3931 | 2016-08-31 | 2016-08-04
VIC | MOUNT BEAUTY | MTBY | CA3 | QMTBYE31M | QMTBYE4001M | DA500 | 3699 | 2016-06-30 | 2016-06-30
NSW | OLD BAR | OBAR | CA17 | QOBARE4001S2 | QOBARE4007M | DA17 | 2430 | 2016-09-16 | 2016-07-26
NSW | OLD BAR | OBAR | CA17 | QOBARE4001S2 | QOBARE4006M | DA17 | 2430 | 2016-09-16 | 2016-07-26
NSW | HARBORD | HARB | CA9 | QHARBE12S2 | QHARBE4011M | DA67;DA151 | 2100 | 2016-09-16 | 2017-08-31 | Y
NSW | PARKES | PRKS | CA57 | QPRKSE4005M | QPRKSE4011M | DA57 | 2600 | 2017-06-30 | 2017-06-01
NSW | PARKES | PRKS | CA57 | QPRKSE4005M | QPRKSE4012M | DA57 | 2600 | 2017-06-30 | 2017-06-01
NSW | FERNHILL | FNHL | CA2 | QFNHLE4005M | QFNHLE4012M | DA86; DA97 | 2444 | 2016-09-16 | 2017-08-31
NSW | FERNHILL | FNHL | CA2 | QFNHLE4005M | QFNHLE4011M | DA86; DA97 | 2444 | 2016-09-16 | 2017-08-31
NSW | WANGI WANGI | WNGI | CA10 | QWNGIE4004M | QWNGIE4011M | DA10 | 2267 | 2016-08-31 | 2016-07-29
NSW | REVESBY | REVE | CA7 |  | QREVEE4016M | DA169;DA44;DA36 | 2213 | 2016-07-31 | 2016-06-30 | Y | REVE-CA7-Area-Layout | REVE-CA7-Map-REVE-DA36 | REVE-CA7-Map-REVE-DA44 | REVE-CA7-Map-REVE-DA169
ACT | MANUKA | MNKA | CA73 | QMNKAE4004M | QMNKAE4014M | DA73; DA77 | 2603 | 2016-08-31 | 2016-08-17 | Y
VIC | NAR NAR GOON NORTH | NNGN | CA2 | QNNGNE43S2 | QNNGNE4002M | DA509 | 3812 | 2016-09-30 | 2016-08-31
VIC | LAKES ENTRANCE | LENT | CA9 | QLENTE3S4 | QLENTE4007M | DA29 | 3909 | 2016-11-30 | 2016-10-12
VIC | WENDOUREE | WEND | CA5 | QWENDE10M | QWENDE4002M | DA33 | 3355 | 2016-12-02 | 2016-12-02 | Y
VIC | WENDOUREE | WEND | CA5 | QWENDE10M | QWENDE4001M | DA33 | 3355 | 2016-12-02 | 2016-12-02 | Y
VIC | HORSHAM | HORM | CA11 | QHORME4M | QHORME4005M | DA78 | 3400 | 2016-09-30 | 2016-10-31
VIC | HORSHAM | HORM | CA11 | QHORME4M | QHORME4004M | DA78 | 3400 | 2016-09-30 | 2016-10-31
QLD | FERNY HILLS | FHLS | CA43 | QFHLSE45M | QFHLSE4014M | DA41; DA43 | 4055 | 2017-02-08 | 2017-01-23
QLD | FERNY HILLS | FHLS | CA43 | QFHLSE45M | QFHLSE4013M | DA41; DA43 | 4055 | 2017-02-08 | 2017-01-23
QLD | BURLEIGH HEADS | BURL | CA6 | QBURLE19M | QBURLE4018M | DA110; DA115 | 4220 | 2016-08-31 | 2016-08-12 | Y
QLD | BURLEIGH HEADS | BURL | CA6 | QBURLE19M | QBURLE4017M | DA110; DA115 | 4220 | 2016-08-31 | 2016-08-12 | Y
QLD | ASHMORE | ASHM | CA85 | QASHME22M | QASHME4015M | DA85 | 4214 | 2016-10-31 | 2016-10-17
QLD | ASHMORE | ASHM | CA85 | QASHME22M | QASHME4014M | DA85 | 4214 | 2016-10-31 | 2016-10-17
NSW | TEA GARDENS | TGNS | CA4 | QTGNSE4001S2 | QTGNSE4009M | DA4 | 2324 | 2016-09-30 | 2016-09-20
NSW | TEA GARDENS | TGNS | CA4 | QTGNSE4001S2 | QTGNSE4010M | DA4 | 2324 | 2016-09-30 | 2016-09-20
NSW | BYRON BAY | BYBY | P14 |  | QBYBYE4010M | DA14 | 2481 |  | 2017-01-31 |  | BYBY-P14-Area-Layout.pdf | BYBY-P14-Map-BYBY-DA14.pdf
QLD | TINGALPA | TGPA | CA76 | QTGPAE60M | QTGPAE4018M | DA76 | 4174 | 2016-12-31 | 2016-12-08
QLD | TINGALPA | TGPA | CA76 | QTGPAE60M | QTGPAE4017M | DA76 | 4174 | 2016-12-31 | 2016-12-08
QLD | ST GEORGE | STGE | CA16 | QSTGEE36M | QSTGEE4002M | DA16 | 4487 | 2016-10-31 | 2016-10-04
QLD | MUDGEERABA | MGBA | CA68 | QMGBAE71M | QMGBAE4026M | DA68 | 4213 |  | 2016-12-13
QLD | MUDGEERABA | MGBA | CA68 | QMGBAE71M | QMGBAE4025M | DA68 | 4213 |  | 2016-12-13
QLD | ROMA | ROMA | CA36 | QROMAE60M | QROMAE4006M | DA36 | 4455 | 2016-10-31 | 2016-09-30
WA | MUNDIJONG | MDJG | CA2 | QMDJGE6S2 | QMDJGE4003M | DA13 | 6123 | 2016-11-30 | 2016-10-10
WA | MUNDIJONG | MDJG | CA2 | QMDJGE6S2 | QMDJGE4002M | DA13 | 6123 | 2016-11-30 | 2016-10-10
WA | MUCHEA | MUCH | CA3 | QMUCHE2S3 | QMUCHE4008M | DA5 | 6501 | 2016-12-31 | 2016-11-12
WA | MUCHEA | MUCH | CA3 | QMUCHE2S3 | QMUCHE4007M | DA5 | 6501 | 2016-12-31 | 2016-11-12
WA | MUCHEA | MUCH | CA1 | QMUCHE5M | QMUCHE4006M | DA500 | 6501 |  | 2016-06-27
WA | MUCHEA | MUCH | CA1 | QMUCHE5M | QMUCHE4005M | DA500 | 6501 |  | 2016-06-27
VIC | MOOROOLBARK | MORK | CA21 | QMORKE115M | QMORKE4006M | DA75; DA88; DA92 | 3116 |  | 2016-05-12 | Y
WA | OYSTER HARBOUR | OYHR | P18 | QOYHRE60M | QOYHRE4006M | DA18 | 6330 | 2016-10-31 | 2016-10-14
WA | OYSTER HARBOUR | OYHR | P18 | QOYHRE60M | QOYHRE4005M | DA18 | 6330 | 2016-10-31 | 2016-10-14
QLD | JAMBOREE HEIGHTS | JREE | CA27 | QJREEE21M | QJREEE4017M | DA82; DA90 | 4073 | 2016-11-30 | 2016-11-02
QLD | NEWMARKET | NMKT | CA22 | QNMKTE32M | QNMKTE4007M | DA22 | 4051 | 2016-11-30 | 2016-10-24
QLD | ROBINA | RBNA | CA16 | QRBNAE37M | QRBNAE4022M | DA26; DA16 | 4227 |  | 2016-12-21
QLD | FRESHWATER | FRES | CA26 | QFRESE19M | QFRESE4004M | DA26 | 4870 | 2016-10-31 | 2016-09-09
QLD | MUDGEERABA | MGBA | CA79 | QMGBAE66M | QMGBAE4027M | DA79 | 4213 | 2016-10-31 | 2016-10-12
QLD | ORMEAU | ORME | CA21 | QORMEE37M | QORMEE4026M | DA20; DA21 | 4208 | 2016-10-31 | 2016-10-12 | Y
QLD | ORMEAU | ORME | CA16 | QORMEE34M | QORMEE4025M | DA16 | 4208 | 2016-10-31 | 2016-10-12
QLD | STEPHENS | SPHS | CA1 | QSPHSE17M | QSPHSE4009M | DA15 | 4227 | 2016-11-30 | 2016-10-13
QLD | ROBINA | RBNA | CA49 | QRBNAE24M | QRBNAE4021M | DA49 | 4226 | 2016-10-31 | 2016-10-18
QLD | NARANGBA | NRBA | P40 |  | QNRBAE4009M | DA40 | 4505 | 2016-11-30 | 2016-10-31 | Y
QLD | NARANGBA | NRBA | P40 |  | QNRBAE4008M | DA40 | 4505 | 2016-11-30 | 2016-10-31 | Y
QLD | ALICE RIVER | ALCR | CA2 | QALCRE16M | QALCRE4002M | DA5; DA12 | 4817 | 2016-10-31 | 2016-09-09 | Y
VIC | SEAFORD | SEAF | CA37 |  | QSEAFE4007M | DA3 | 3198 | 2016-08-31 | 2016-07-28 | Y
QLD | TINGALPA | TGPA | CA74 | QTGPAE53M | QTGPAE4019M | DA74 | 4172 | 2016-11-30 | 2016-10-14
QLD | HIGHFIELDS | HFDS | CA15 | QHFDSE36M | QHFDSE4012M | DA15 | 4352 | 2016-11-30 | 2016-10-28
QLD | EIGHT MILE PLAINS | EMPS | CA96 | QEMPSE70M | QEMPSE4015M | DA90 | 4112 | 2016-11-30 | 2016-10-17 | Y
QLD | WYNNUM | WYNM | CA122 | QWYNME122M | QWYNME4014M | DA137; DA122 | 4178 | 2016-12-31 | 2016-11-22 | Y
VIC | BENDIGO | BEND | CA6 | QBENDE5M | QBENDE4006M | DA204 | 3555 | 2016-10-31 | 2016-09-30
SA | LONSDALE | LSDE | P147 | QLSDEE103M | QLSDEE4016M | DA147 | 5167 | 2017-03-31 | 2017-02-22
SA | HENLEY BEACH | HNLY | CA34 | QHNLYE95M | QHNLYE4008M | DA166 | 5022 | 2017-03-31 | 2017-02-17 | Y
SA | GEPPS CROSS | GPCS | CA46 | QGPCSE86M | QGPCSE4023M | DA84 | 5098 | 2017-02-28 | 2017-02-16
SA | LONSDALE | LSDE | CA19 | QLSDEE102M | QLSDEE4017M | DA179 | 5168 | 2017-03-31 | 2017-03-01
QLD | CURTIS | CURT | CA100 | QCURTE22M | QCURTE4008M | DA100; DA3 | 4680 | 2016-11-30 | 2016-11-01 | Y
QLD | NOOSAVILLE | NOOV | CA35 | QNOOVE31M | QNOOVE4013M | DA35 | 4565 | 2016-11-30 | 2016-11-03
QLD | WARWICK | WARW | CA80 | QWARWE65M | QWARWE4001M | DA80 | 4370 | 2016-11-30 | 2016-10-24
QLD | TAMBORINE VILLAGE | TBNE | CA10 | QTBNEE29M | QTBNEE4006M | DA10; DA2 | 4270 |  | 2016-11-14
QLD | TAMBORINE VILLAGE | TBNE | CA1 | QTBNEE28M | QTBNEE4005M | DA1; DA6 | 4270 |  | 2016-12-09
VIC | YARRAWONGA | YWGA | CA4 | QYWGAE18M | QYWGAE4003M | DA37; DA34; DA28 | 3730 | 2017-03-31 | 2017-01-31
VIC | MILDURA | MILD | CA19 | QMILDE8M | QMILDE4011M | DA119; DA123 | 2739 | 2017-02-10 | 2017-01-20
VIC | HORSHAM | HORM | CA4 | QHORME3M | QHORME4007M | DA69 | 3400 | 2017-02-24 | 2017-07-28
VIC | HORSHAM | HORM | P66 | QHORME5M | QHORME4006M | DA66 | 3400 | 2017-02-28 | 2016-12-15
VIC | BELMONT | BELM | CA6 | QBELME103M | QBELME4013M | DA124 | 3216 | 2016-11-30 | 2016-10-25
VIC | BELMONT | BELM | CA2 | QBELME102M | QBELME4012M | DA120 | 3216 | 2016-10-31 | 2016-11-25
QLD | BLI BLI | BLIB | CA7 | QBLIBE21M | QBLIBE4005M | DA17; DA9; DA7 | 4559 | 2016-12-31 | 2016-12-06 | Y
QLD | OXENFORD | OXEN | CA118 | QOXENE90M | QOXENE4080M | DA118; DA173 | 4211 | 2016-11-30 | 2016-11-04 | Y
NSW | TENNYSON | TNYN | CA1 | QTNYNE4002M | QTNYNE4004M | DA16 | 2754 | 2016-12-31 | 2016-12-16
NSW | KURRAJONG | KURG | CA2 | QKURGE4003M | QKURGE4007M | DA19 | 2758 | 2016-12-31 | 2016-12-05
NSW | MILLER | MILL | CA24 | QMILLE4001M | QMILLE4057M | DA532;DA551;DA552 | 2171 | 2016-07-31 | 2016-06-30 | Y
QLD | HATTON VALE | HATT | CA26 | QHATTE40M | QHATTE4003M | DA26; DA27 | 4341 | 2016-11-30 | 2016-10-21
SA | COROMANDEL VALLEY | CLVY | P81 | QCLVYE67M | QCLVYE4007M | DA81 | 5159 | 2017-03-31 | 2017-02-24 | Y
QLD | LOWOOD | LOWO | CA9 | QLOWOE25M | QLOWOE4002M | DA9; DA12 | 4311 | 2016-11-30 | 2016-11-16
VIC | LAVERTON | LTVN | CA10 | QLTVNE25M | QLTVNE4027M | DA22; DA25; DA29; DA31 | 3028 | 2017-03-31 | 2017-01-30 | Y
WA | KARRATHA | KAHA | CA4 | QKAHAE61S2 | QKAHAE4007M | DA26;DA27 | 6714 | 2016-11-30 | 2016-10-24
WA | BROOME | BRMK | CA3 | QBRMKE74M | QBRMKE4010M | DA37 | 6725 | 2016-11-30 | 2016-11-03
NT | KATHERINE | KTHN | CA71 | QKTHNE8S1 | QKTHNE4008M | DA71 | 853 | 2016-09-30 | 2016-07-28
NSW | EASTWOOD | EWOO | CA4 | QEWOOE4002M | QEWOOE4011M | DA172 | 2118 | 2016-10-31 | 2016-10-05 | Y
NSW | EASTWOOD | EWOO | CA4 | QEWOOE4002M | QEWOOE4010M | DA172 | 2118 | 2016-10-31 | 2016-10-05 | Y
QLD | TAMBORINE MOUNTAIN | TBNM | CA3 | QTBNME40M | QTBNME4006M | DA8; DA24; DA25 | 4272 | 2016-09-30 | 2016-09-09
WA | BEECHBORO | BCHS | P30 | QBCHSE17M | QBCHSE4005M | DA30 | 6063 | 2016-12-31 | 2016-12-14
WA | ROCKINGHAM | RKHM | CA10 | QRKHME68M | QRKHME4023M | DA96 | 6168 | 2016-12-31 | 2016-12-06 | Y
QLD | NOOSAVILLE | NOOV | CA71 | QNOOVE32M | QNOOVE4015M | DA71; DA59 | 4565 | 2016-12-31 | 2016-12-13
WA | JANDAKOT SOUTH | JTSX | CA7 | QJTSXE3S8 | QJTSXE4021M | DA57;DA58 | 6164 | 2016-12-31 | 2016-12-16
WA | MORLEY | MLEY | P108 | QMLEYE112M | QMLEYE4010M | DA108 | 6062 | 2016-12-31 | 2016-12-13
WA | MADDINGTON | MADD | P16 | QMADDE3M | QMADDE4011M | DA16 | 6109 | 2016-12-31 | 2016-12-08 | Y
WA | HERNE HILL | HERL | P12 | QHERLE101M | QHERLE4005M | DA12 | 6056 | 2016-12-31 | 2016-12-15
VIC | CORIO | CORI | CA1 | QCORIE4M | QCORIE4006M | DA60; DA61 | 3214 | 2017-08-31 | 2016-09-30
VIC | BACCHUS MARSH | BACC | CA7 | QBACCE4S5 | QBACCE4004M | DA500 | 3340 | 2017-12-16 | 2016-11-30
TAS | SOUTH BRUNY | SBRY | CA1 |  | QSBRYE4001M | DA500 | 7150 | 2017-04-30 | 2017-03-31
VIC | MORDIALLOC | MLOC | CA13 | QMLOCE112M | QMLOCE4007M | DA118 | 3195 | 2016-10-31 | 2016-09-17
WA | MOUNT HELENA | MTNA | P7 | QMTNAE4M | QMTNAE4003M | DA7 | 6082 | 2016-12-16 | 2016-12-12 | Y
WA | BALDIVIS | BALD | CA5 | QBALDE7M | QBALDE4021M | DA4;DA41 | 6171 |  | 2016-12-21
WA | CAPEL | CAPL | CA1 | QCAPLE6M | QCAPLE4003M | DA9;DA10 | 6271 | 2016-12-31 | 2016-11-28
WA | BUSSELTON | BUSS | P3 | QBUSSE25M | QBUSSE4016M | DA3 | 6280 | 2016-12-31 | 2016-12-19 | Y
WA | DUNSBOROUGH | DBGH | CA20 | QDBGHE10M | QDBGHE4010M | DA20 | 6281 | 2016-12-31 | 2016-11-18
NSW | NARELLAN | NRLN | G101 |  | QNRLNE4047M | DA401 | 2567 |  | 2015-11-30 |  | NRLN-G101-Area-Layout.pdf | NRLN-G101-Map-NRLN-DA401.pdf
QLD | INGLESIDE | INGS | CA5 | QINGSE27M | QINGSE4001M | DA5 | 4228 | 2017-05-31 | 2017-01-03
QLD | KURANDA | KURA | CA11 | QKURAE8M | QKURAE4002M | DA7; DA11 | 4872 | 2016-12-31 | 2016-12-14 | Y
NSW | CESSNOCK | CESS | CA78 | QCESSE4001S4 | QCESSE4020M | DA74; DA78 | 2325 | 2016-12-31 | 2016-11-30
NSW | LAKE CATHIE | LCAT | CA16 | QLCATE4004M | QLCATE4007M | DA16; DA17 | 2445 |  | 2016-12-19
ACT | MELBA | MLBA | CA79 | QMLBAE4016M | QMLBAE4039M | DA79; DA87 | 2615 | 2016-10-31 | 2016-09-15
ACT | MELBA | MLBA | CA71 | QMLBAE4014M | QMLBAE4038M | DA71; DA80; DA86 | 2615 | 2016-10-31 | 2016-09-07
ACT | MELBA | MLBA | CA73 | QMLBAE4009M | QMLBAE4037M | DA70; DA73 | 2615 | 2016-10-31 | 2016-10-06
ACT | MELBA | MLBA | CA74 | QMLBAE4013M | QMLBAE4036M | DA74; DA76 | 2615 | 2016-11-30 | 2016-10-26
QLD | PIALBA | PLBA | CA93 | QPLBAE69M | QPLBAE4027M | DA41; DA45; DA129 | 4655 | 2017-06-30 | 2017-05-23 | Y
VIC | ROSEBUD | ROSB | CA20 | QROSBE8M | QROSBE4015M | DA102 | 3939 | 2017-08-31 | 2016-10-28
VIC | ELAINE | ELAI | CA1 | QELAIE2S2 | QELAIE4001M | DA501 | 3334 | 2017-04-30 | 2017-02-09
WA | HAMERSLEY | HAMS | CA8 | QHAMSE19M | QHAMSE4022M | DA104;DA122;DA123;DA124;DA125;DA126 | 6020 | 2016-11-30 | 2016-09-23
WA | LITTLE GROVE | LTLG | CA6 | QLTLGE1M | QLTLGE4001M | DA6 | 6330 | 2017-01-31 | 2016-12-20
QLD | DALBY | DABX | CA56 | QDABXE82M | QDABXE4007M | DA56 | 4405 | 2017-01-31 | 2016-12-30
VIC | MERNDA | MRDA | CA12 | QMRDAE4S7 | QMRDAE4022M | DA28; DA52 | 3754 | 2017-10-31 | 2017-09-29
QLD | WYNNUM | WYNM | CA101 | QWYNME43S5 | QWYNME4015M | DA99; DA145 | 4178 | 2016-12-31 | 2016-12-14
ACT | MELBA | MLBA | CA70 | QMLBAE4015M | QMLBAE4035M | DA70 | 2615 | 2017-04-28 | 2017-02-07
NSW | PORT MACQUARIE | PTMA | CA108 | QPTMAE4005M | QPTMAE4034M | DA108 | 2444 | 2017-01-31 | 2017-01-31
WA | BROOME | BRMK | P35 | QBRMKE77M | QBRMKE4009M | DA35 | 6725 | 2016-11-30 | 2016-11-02
NSW | LLANDILO | LLDO | CA1 | QLLDOE4015M | QLLDOE4017 | DA3;DA10 | 2749 | 2016-04-30 | 2016-05-31
NSW | NARELLAN | NRLN | CA57 | QNRLNE4003M | QNRLNE4056 | DA57 | 2567 | 2016-04-30 | 2016-05-12
WA | BROOME | BRMK | P36 | QBRMKE2M | QBRMKE4008M | DA36 | 6725 | 2016-11-30 | 2016-10-26 | Y
VIC | WOLLERT | WLRT | G12A | QWLRTE4002M | QWLRTE4006M | DA12 | 3750 |  | 2017-09-29
NSW | SINGLETON HEIGHTS | SNHS | CA60 | QSNHSE4003M | QSNHSE4011M | DA60 | 2330 | 2017-01-31 | 2016-12-07
QLD | KALLANGUR | KLGR | CA138 | QKLGRE47S7 | KLGRE4034M | DA130; DA137 | 4509 | 2016-12-31 | 2016-11-29
QLD | SANDGATE | SDTE | CA19 |  | QSDTEE4009M | DA13; DA19; DA57; DA67 | 4017 | 2017-01-31 | 2016-11-15
QLD | DOONAN | DNAN | CA13 | QDNANE11M | QDNANE4004M | DA11; DA13 | 4562 |  | 2016-12-05 | Y
QLD | HADDON | HADN | CA3 |  | QHADNE4001M | DA500 | 4482 | 2017-07-31 | 2017-06-08
NSW | MILLER | MILL | G647 |  | QMILLE4056M | DA647 | 2171 | 2016-10-31 | 2016-10-06
WA | GREENMOUNT | GRMT | CA3 | QGRMTE41M | QGRMTE4003M | DA30 | 6056 | 2017-08-31 | 2017-07-07
WA | GREENMOUNT | GRMT | CA3 | QGRMTE14M | QGRMTE4003M | DA30 | 6056 | 2017-08-31 | 2017-07-07
NSW | QUEANBEYAN | QNBN | CA93 | QQNBNE4005M | QQNBNE4021M | DA93 | 2620 | 2017-08-31 | 2017-07-17
NSW | QUEANBEYAN | QNBN | CA93 | QQNBNE4005M | QQNBNE4021M | DA93 | 2621 | 2017-08-31 | 2017-07-17
QLD | NAMBOUR | NBUR | G70 |  | QNBURE4011M | DA70 | 4560 | 2017-06-30 | 2017-06-04
VIC | TARNEIT | TNIT | CA14 | QTNITE2S2 | QTNITE4033M | DA111; DA112 | 3029 |  | 2017-09-20
VIC | POINT COOK | PCOK | G97 |  | QPCOKE4038M | DA93, DA95; DA97 | 3030 |  | 2017-10-26
WA | BROOME | BRMK | G43 |  | QBRMKE4011M | DA43 | 6725 |  | 2017-07-27
WA | JANDAKOT SOUTH | JTSX | CA9 | QJTSXE3S3 | QJTSXE4022M | DA62 | 6164 | 2017-06-30 | 2017-06-09
ACT | BARTON | BRTN | G46 |  | QBRTNE4005M | DA46 | 2612 | 2017-09-30 | 2017-07-17
VIC | LAVERTON | LTVN | CA28 | QLTVNE4S2 | QLTVNE4028M | DA107; DA126; DA125; DA126 | 3030 |  | 2017-09-18
QLD | THORNLANDS | THOR | CA33 | QTHORE14S3 | QTHORE4004M | DA18, DA34 | 4157 | 2017-05-31 | 2017-04-26
QLD | SWANBANK | SWBK | CA40 | QSWBKE6S2M | QSWBKE4009M | DA37, DA46 | 4306 | 2017-05-31 | 2017-04-26
QLD | TORQUAY | TQAY | CA60 | QTQAYE3S3M | QTQAYE4008M | DA46, DA61, DA64 | 4655 | 2017-06-30 | 2017-05-30
QLD | ROTHWELL | RTWL | CA52 | QRTWLE7S2M | QRTWLE4014M | DA52 | 4508 | 2017-05-31 | 2017-04-21
WA | MADDINGTON | MADD | CA5 | QMADDE25M | QMADDE4013M | DA6;DA7 | 6109 | 2017-08-31 | 2017-06-28
WA | BALDIVIS | BALD | CA60 | QBALDE29M | QBALDE4023M | DA60 | 6171 | 2017-06-30 | 2017-06-29
WA | GOSNELLS | GOSN | CA8 | QGOSNE4S2 | QGOSNE4013M | DA70 | 6110 | 2017-08-31 | 2017-07-21
VIC | MILDURA | MILD | CA23 | QMILDE13S3 | QMILDE4012M | DA130 | 3500 | 2017-10-31 | 2017-09-18
NSW | PORT MACQUARIE | PTMA | CA119 | QPTMAE4001S5 | QPTMAE4035M | DA119 | 2324 | 2017-06-30 | 2017-06-30
VIC | BELMONT | BELM | CA9 | QBELME6S4 | QBELME4009M | DA126; DA135 | 3216 | 2017-09-30 | 2017-08-03
WA | WANNEROO | WANO | CA4 | QWANOE3S4 | QWANOE4028M | DA48 | 6031 | 2017-08-31 | 2017-08-31 |  | GUNN-P48-Area-Layout.pdf | GUNN-P48-Map-GUNN-DA48.pdf
WA | WANNEROO | WANO | CA14 | QWANOE3S7 | QWANOE4027M | DA116;DA121 | 6065 | 2017-06-30 | 2017-06-29
WA | WANNEROO | WANO | CA11 | QWANOE3S3 | QWANOE4026M | DA46;DA47 | 6077 | 2017-06-30 | 2017-07-04
VIC | BELMONT | BELM | CA4 | QBELME4S1 | QBELME4014M | DA64; DA128 | 3216 |  | 2018-03-15
WA | YANCHEP | YANP | CA4 | QYANPE3S2 | QYANPE4007M | DA112;DA115 | 6037 | 2017-06-30 | 2017-06-23
WA | CANNING VALE | CNVL | CA9 | QCNVLE30S7 | QCNVLE4021M | DA101 | 6155 | 2017-06-30 | 2017-06-16
NT | VICTORIA RIVER | VIER | S22 |  | QVIERE4007M |  | 852 | 2019-03-15 | 2019-03-15
NT | ALYANGULA | AYLB | S2 |  | QAYLBE4003M | DA901 | 822 |  | 2018-01-26
NT | ROPER RIVER | ROPR | S318 |  | QROPRE4003M | DA901 | 852 |  | 2017-12-15
NT | PETERMANN | PETN | P80 | QPETNE4008M | QPETNE4008M | DA80 | 872 |  | 2017-10-20
VIC | COBURG | CBRG | CA16 | QCBRGE10S2 | QCBRGE4002M | DA70 | 3058 |  | 2017-09-20
WA | TUART HILL | TUTT | CA1 | QTUTTE7M | QTUTTE4009M | DA112;DA113:DA117:DA119:DA128 | 6059 | 2017-06-30 | 2017-06-17
WA | FORRESTFIELD | FRFD | CA2 | QFRFDE4S3 | QFRFDE4003M | DA42 | 6107 | 2017-07-31 | 2017-06-20
WA | TUART HILL | TUTT | CA2 | QTUTTE13M | QTUTTE4007M | DA73;DA74 | 6060 | 2017-09-30 | 2017-08-02
WA | TUART HILL | TUTT | CA2 | QTUTTE13M | QTUTTE4008M | DA73;DA74 | 6060 | 2017-09-30 | 2017-08-02
QLD | PIALBA | PLBA | CA52 | QPLBAE68M | QPLBAE4029M | DA51; DA52 | 4655 | 2017-06-30 | 2017-05-18
QLD | PIALBA | PLBA | CA116 | QPLBAE24S2 | QPLBAE4028M | DA63; DA123 | 4655 | 2017-06-30 | 2017-05-25
VIC | FINGAL | FING | P43 |  | QFINGE4003M | DA43 | 3939 | 2017-08-31 | 2017-08-02
QLD | GLASSHOUSE MOUNTAINS | GHMT | CA10 | QGHMTE4001 | QGHMTE4007M | DA10 | 4518 | 2017-07-31 | 2017-06-21
NSW | WANGI WANGI | WNGI | CA2 | QWNGIE4006M | QWNGIE4012M | DA2; DA28 | 2267 |  | 2018-03-28
QLD | GLASSHOUSE MOUNTAINS | GHMT | CA10 | QGHMTE4001 | QGHMTE4006M | DA10 | 4518 | 2017-07-31 | 2017-06-21
QLD | ROBINA | RBNA | CA84 | QRBNAE22S4 | QRBNAE4024M | DA84; DA85; DA86 | 4226 | 2017-07-31 | 2017-06-16
QLD | ROBINA | RBNA | CA32 | QRBNAE38M | QRBNAE4025M | DA32; DA47 | 4226 | 2017-07-31 | 2017-06-23
NSW | MEDOWIE | MDWI | CA25 | QMDWIE4001S2 | QMDWIE4011M | DA25; DA27 | 2318 |  | 2017-08-18
ACT | CIVIC | CVIC | CA134 | QCVICE32S4 | QCVICE4020M | DA134 | 2609 | 2017-08-31 | 2017-08-16
ACT | CIVIC | CVIC | CA134 | QCVICE32S4 | QCVICE4019M | DA134 | 2609 | 2017-08-31 | 2017-08-16
QLD | SAMFORD | SAOD | CA25 | QSAODE66M | QSAODE4009M | DA19 | 4055 | 2017-07-31 | 2017-07-14
QLD | GATTON | GATT | CA34 | QGATTE6S3 | QGATTE4006M | DA35; DA20; DA29 | 4343 | 2017-07-31 | 2017-06-20
QLD | CURRUMBIN CREEK | CBCK | P4 |  | QCBCKE4002M | DA4 | 4223 | 2017-07-31 | 2017-06-15
QLD | CLEVELAND | CLVL | CA85 | QCLVLE49M | QCLVLE4009M | DA13; DA14; DA81; DA62 | 4160 | 2017-07-31 | 2017-06-30
VIC | WALLAN | WLAN | CA1 | QWLANE2M | QWLANE4005M | DA500 | 3756 | 2017-09-30 | 2017-08-29
WA | DENMARK | DENK | P15 | QDENKE7M | QDENKE4006M | DA15 | 6333 | 2017-09-30 | 2017-08-17
WA | MUNSTER | MUNS | CA6 | QMUNSE16S5 | QMUNSE4015M | DA5 | 6164 | 2017-08-31 | 2017-08-31
WA | FORRESTFIELD | FRFD | CA1 | QFRFDE4S2 | QFRFDE4004M | DA15 | 6058 | 2017-08-31 | 2017-07-14
WA | CANNING VALE | CNVL | CA7 | QCNVLE30S4 | QCNVLE4022M | DA94; DA110 | 6155 | 2017-07-31 | 2017-07-06
WA | BALDIVIS | BALD | CA17 | QBALDE60S5 | QBALDE4024M | DA25; DA43 | 6171 | 2017-08-31 | 2017-07-13
NSW | SANCTUARY POINT | SANP | CA25 | QSANPE4004M | QSANPE4011M | DA13; DA25 | 2540 |  | 2017-09-07 | Y
QLD | THURSDAY ISLAND | THUR | CA1 | QTHURE68M | QTHURE4002M |  | 4875 | 2017-09-30 | 2017-08-25
NT | ROPER RIVER | ROPR | S64 |  | QROPRE04006M | DA1 | 0852 |  | 2018-05-10
NSW | TORONTO | TRTO | CA43 | QTRTOE4005M | QTRTOE4025M | DA1;DA26;DA50 | 2283 |  | 2018-04-13 | Y
QLD | SAMFORD | SAOD | P12 |  | QSAODE4010M | DA12 | 4520 | 2017-10-31 | 2017-09-04 | Y
ACT | BELCONNEN | BLCN | CA70 | QBLCNE7S2 | QBLCNE4017M | DA70; DA71 | 2617 |  | 2018-05-25
NSW | KOORINGAL | KRGL | CA45 | QKRGLE4001S4 | QKRGLE4019M | DA45 | 2650 |  | 2018-04-06
QLD | CLEVELAND | CLVL | CA98 | QCLVLE3/S4 | QCLVLE4010M | DA95; DA97 | 4163 | 2017-12-31 | 2017-11-02
WA | ELLENBROOK | ELBK | CA21 | QELBKE4004S2 | QELBKE4013M | DA77 | 6069 | 2017-12-31 | 2017-11-20
QLD | MORAYFIELD | MRFD | CA44 | QMRFDE1S6 | QMRFDE4013M | DA37; DA45 | 4506 | 2017-12-31 | 2017-11-17
QLD | MORAYFIELD | MRFD | CA40 | QMRFDE1S2 | QMRFDE4014M | DA39 | 4506 | 2017-12-31 | 2017-11-14
NSW | KOORINGAL | KRGL | CA63 | QKRGLE4001S3 | QKRGLE4019M | DA63; DA71 | 2650 |  | 2018-07-02
QLD | HADDON | HADN | CA3 |  | QHADNE4001M | DA500;DA503 | 4483 | 2017-07-31 | 2017-06-08
VIC | WARRANWOOD | WRWD | P21 | QWRWDE4003M | QWRWDE4003M | DA21 | 3134 |  | 2018-03-01 | Y
VIC | WARRANWOOD | WRWD | P21 | QWRWDE4003M | QWRWDE4004M | DA21 | 3134 |  | 2018-03-01 | Y
NSW | LAGUNA | LAGA | CA5 | QLAGAE4001S3 | QLAGAE4006M | DA5 | 2325 |  | 2018-03-13
NSW | LAGUNA | LAGA | CA1 | QLAGAE4003M | QLAGAE4005M | DA500 | 2325 |  | 2018-03-22
QLD | MARSDEN | MRDN | G51 |  | QMRDNE4011M | DA51 | 4125 |  | 2018-02-21
QLD | BEECHMONT | BHMT | CA2 | QBHMTE13M | QBHMTE4002M | DA2 | 4211 |  | 2017-11-21
NSW | MACLEAN | MCLN | CA17 | QMCLNE4001S2 | QMCLNE4013M | DA17; DA34 | 2463 |  | 2018-05-03
NSW | MACLEAN | MCLN | CA17 | QMCLNE4001S2 | QMCLNE4012M | DA17; DA34 | 2463 |  | 2018-05-03
QLD | WEIPA | WEPD | CA1 | QWEPDE3S3 | QWEPDE4003M | DA5; DA6 | 4874 |  | 2017-11-24
VIC | NARRE WARREN NORTH | NARN | CA3 | QNARNE4M | QNARNE4006M | DA4 | 3804 |  | 2018-03-29
VIC | NARRE WARREN NORTH | NARN | CA3 | QNARNE4M | QNARNE4005M | DA4 | 3804 |  | 2018-03-29
ACT | HALL | HALL | CA5 | QHALLE4002M | QHALLE4008M | DA5 | 2618 |  | 2018-06-08
VIC | COBRAM | COBM | CA6 | QCOBME50S2 | QCOBME4004M | DA500 | 3644 |  | 2018-04-06
WA | GREENMOUNT | GRMT | P4 | QGRMTE7M | QGRMTE4004M | DA4 | 6056 |  | 2017-12-11
WA | HERNE HILL | HERL | P14 | QHERLE2M | QHERLE4006M | DA14 | 6055 |  | 2017-11-30
VIC | TYLDEN | TYLD | CA1 | QTYLDE11S2 | QTYLDE11S2 | DA500 | 3444 |  | 2018-03-27
NSW | GUNNEDAH | GUNN | P48 | QGUNNE4009M |  | DA48 | 2380 |  | 2017-11-21
WA | ELLENBROOK | ELBK | CA2 | QELBKE6M | QELBKE6M | DA22; DA23; DA24 | 6055 |  | 2018-03-02
WA | MIDLAND | MDLD | CA5 | QMDLDE9M | QMDLDE9M | DA42;DA44 | 6056 |  | 2018-02-26
QLD | BAFFLE CREEK | BAFF | CA9 | QBAFFE24M | QBAFFE4001M | DA11;DA12 | 4670 |  | 2018-03-23
QLD | BAFFLE CREEK | BAFF | CA10 | QBAFFE22M | QBAFFE4002M | DA7; DA1 | 4670 |  | 2018-03-27
WA | EXMOUTH | EXMH | T80 | QEXMHE4002M | QEXMHE9831 | DA0 | 6707 |  | 2017-11-24
QLD | NOOSAVILLE | NOOV | CA74 | QNOOVE1S3 | QNOOVE4016M | DA33 | 4565 |  | 2018-03-23
WA | KUNUNURRA | KNRF | CA2 | QKNRFE111M | QKNRFE4006M | DA18 | 6743 |  | 2018-03-23
WA | KUNUNURRA | KNRF | CA2 | QKNRFE111M | QKNRFE4005M | DA18 | 6743 |  | 2018-03-23
NSW | SPENCER | SPCR | CA6 | QSPCRE4002M | QSPCRE4004M | DA0 | 2775 |  | 2018-04-04
NSW | SPENCER | SPCR | CA3 | QSPCRE4001S2 | QSPCRE4005M | DA3 | 2775 |  | 2018-03-29
WA | MORLEY | MLEY | P50 | QMLEYE115M | QMLEYE4012M | DA50 | 6059 |  | 2018-03-07
WA | GIRRAWHEEN | GIRR | CA3 | QGIRRE7M | QGIRRE4015M | DA80; DA82; DA83; DA88 | 6064 | 2018-04-30 | 2018-03-28
WA | KUNUNURRA | KNRF | CA4 | QKNRFE97S2 | QKNRFE4007M | DA10 | 6743 | 2018-04-30 | 2018-03-23
QLD | TINGALPA | TGPA | CA2 |  | QTGPAE4020M | DA3; DA5; DA32 | 4172 | 2017-12-14 | 2017-12-08
WA | MUNDARING | MDNG | P12 |  | QMDNGE4004M | DA12 | 6081 |  | 2018-03-23
SA | WOODVILLE | WDVL | P12 | QWDVLE45M | QWDVLE45M | DA12 | 5009 |  | 2018-03-08
NT | PLENTY | PLNY | P5 |  | QPLNYE4009M | DA005 | 872 | 2019-06-30 | 2019-05-28
WA | CANNINGTON | CANN | G150 |  | QVICPE4005M | DA150 | 6100 | 2008-09-30 | 2018-11-16
NSW | MEREWETHER | MERE | G10 |  | QMEREE4011M | DA10 | 2291 | 2019-06-30 | 2019-04-03
NSW | VALENTINE | VLTN | G33 |  | QVLTNE4012M | DA33 | 2280 | 2019-09-30 | 2019-09-30
NSW | BUNGWAHL | BWHL | G4 |  | QBWHLE4004M | DA5; DA901 | 2423 | 2018-10-31 | 2018-09-28
NSW | SPENCER | SPCR | CA6 |  | QSPCRE4006M | DA6 | 2775 | 2019-02-28 | 2019-02-13
VIC | KARINGAL | KALG | G105 |  | QKALGE4014M | DA105 | 3910 | 2019-09-30 | 2019-09-06
QLD | WINDAROO | WNRO | G20 |  | QWNROE4003M | DA20 | 4207 | 2019-09-30 | 2019-07-05
QLD | BEACHMERE | BHME | G20 |  | QBHMEE4002M | DA20 | 4510 | 2019-09-30 | 2019-07-11
NSW | ANNA BAY | ANNA | G11 |  | QANNAE4004M | DA11 | 2316 | 2020-06-30 | 2020-07-27

## Record of Issues
Proposed CAN DSLAMs
Issue 267
2021-03-02
External Distribution
Record of Issues
Issue Number | Date | Nature of Amendment
1 | 2013-10-10 | New version of report
2 | 2013-10-22 | Regular Update
4 | 2013-11-05 | Regular Update
5 | 2013-11-12 | Regular Update
6 | 2013-11-10 | Regular Update
8 | 2013-12-03 | Regular Update
9 | 2013-12-10 | Regular Update
10 | 2013-12-17 | Mernda & Somerton added
11 | 2013-12-23 | Regular Update
12 | 2014-01-14 | Regular Update
13 | 2014-01-21 | Regular Update
14 | 2014-01-28 | Regular Update
15 | 2014-02-04 | Regular Update
16 | 2014-02-11 | Regular Update
17 | 2014-02-18 | Regular Update
18 | 2014-02-25 | Regular Update
19 | 2014-03-13 | Regular Update
20 | 2014-03-21 | Regular Update
21 | 2014-03-27 | Regular Update
22 | 2014-04-02 | Regular Update
23 | 2014-04-09 | Regular Update
24 | 2014-04-16 | Regular Update
25 | 2014-05-07 | Regular Update
26 | 2014-05-21 | Regular Update
27 | 2014-05-28 | Regular Update
28 | 2014-06-04 | Regular Update
29 | 2014-06-11 | Regular Update
30 | 2014-06-18 | Regular Update
31 | 2014-06-25 | Regular Update
32 | 2014-07-03 | Regular Update
33 | 2014-07-09 | Regular Update
34 | 2014-07-16 | Regular Update
35 | 2014-07-23 | Regular Update
36 | 2014-07-31 | Regular Update
37 | 2014-08-29 | Regular Update
38 | 2014-09-10 | Regular Update
39 | 2014-09-24 | Regular Update
40 | 2014-09-30 | Regular Update
41 | 2014-10-08 | Regular Update
42 | 2014-10-15 | Regular Update
43 | 2014-10-22 | Regular Update
44 | 2014-10-29 | Regular Update
45 | 2014-11-05 | Regular Update
46 | 2014-11-12 | Regular Update
47 | 2014-11-19 | Regular Update
48 | 2014-12-01 | Regular Update
49 | 2014-12-10 | Regular Update
50 | 2014-12-22 | Regular Update
51 | 2015-01-15 | Regular Update
52 | 2015-01-29 | Regular Update
53 | 2015-02-05 | Regular Update
54 | 2015-02-12 | Regular Update
55 | 2015-02-19 | Regular Update
56 | 2015-02-26 | Regular Update
57 | 2015-03-05 | Regular Update
58 | 2015-03-19 | Regular Update
59 | 2015-03-26 | Regular Update
60 | 2015-04-09 | Regular Update
61 | 2015-04-16 | Regular Update
62 | 2015-04-23 | Regular Update
63 | 2015-04-30 | Regular Update
64 | 2015-05-07 | Regular Update
65 | 2015-05-14 | Regular Update
66 | 2015-05-21 | Regular Update
67 | 2015-05-28 | Regular Update
68 | 2015-06-04 | Regular Update
69 | 2015-06-11 | Regular Update
70 | 2015-06-18 | Regular Update
71 | 2015-06-25 | Regular Update
72 | 2015-07-02 | Regular Update
73 | 2015-07-03 | Regular Update
74 | 2015-07-16 | Regular Update
75 | 2015-07-23 | Regular Update
76 | 2015-07-30 | Regular Update
77 | 2015-08-06 | Regular Update
78 | 2015-08-13 | Regular Update
79 | 2015-08-20 | Regular Update
80 | 2015-08-27 | Regular Update
81 | 2015-09-10 | Regular Update
82 | 2015-09-17 | Regular Update
83 | 2015-09-24 | Regular Update
84 | 2015-10-01 | Regular Update
85 | 2015-10-08 | Regular Update
86 | 2015-10-15 | Regular Update
87 | 2015-10-22 | Regular Update
88 | 2015-10-29 | Regular Update
89 | 2015-11-05 | Regular Update
90 | 2015-11-12 | Regular Update
91 | 2015-11-19 | Regular Update
92 | 2015-11-26 | Regular Update
93 | 2015-12-03 | Regular Update
94 | 2015-12-10 | Regular Update
95 | 2015-12-17 | Regular Update
96 | 2015-12-22 | Regular Update
97 | 2016-01-21 | Regular Update
98 | 2016-01-28 | Regular Update
99 | 2016-02-04 | Regular Update
100 | 2016-02-11 | Regular Update
101 | 2016-02-18 | Regular Update
102 | 2016-03-03 | Regular Update
103 | 2016-03-10 | Regular Update
104 | 2016-03-17 | Regular Update
105 | 2016-03-24 | Regular Update
106 | 2016-03-31 | Regular Update
107 | 2016-04-07 | Regular Update
108 | 2016-04-14 | Regular Update
109 | 2016-04-21 | Regular Update
110 | 2016-04-28 | Regular Update
111 | 2016-05-05 | Regular Update
112 | 2016-05-12 | Regular Update
113 | 2016-05-19 | Regular Update
114 | 2016-05-23 | Map added for QBAXRE4
115 | 2016-05-23 | Map URL correction
116 | 2016-05-26 | Regular update
117 | 2016-06-02 | Regular update
118 | 2016-06-09 | Regular update
119 | 2016-06-16 | Regular update
120 | 2016-06-23 | Regular update
121 | 2016-06-30 | Regular update
122 | 2016-07-07 | Regular update
123 | 2016-07-14 | Regular update
124 | 2016-07-21 | Regular update
125 | 2016-07-28 | Regular update
126 | 2016-08-04 | Regular update
127 | 2016-08-11 | Regular update
128 | 2016-08-18 | Regular update
129 | 2016-08-25 | Regular update
130 | 2016-09-01 | Regular update
131 | 2016-09-08 | Regular update
132 | 2016-09-15 | Regular update
133 | 2016-09-22 | Regular update
134 | 2016-09-29 | Regular update
135 | 2016-10-06 | Regular update
136 | 2016-10-13 | Regular update
137 | 2016-10-20 | Regular update
138 | 2016-10-27 | Regular update
139 | 2016-11-03 | Regular update
140 | 2016-11-10 | Regular update
141 | 2016-11-17 | Regular update
142 | 2016-11-24 | Regular update
143 | 2016-12-01 | Regular update
144 | 2016-12-15 | Regular update
145 | 2016-12-21 | Regular update
146 | 2017-01-12 | Regular update
147 | 2017-01-19 | Regular update
148 | 2017-01-25 | Regular update
149 | 2017-02-02 | Regular update
150 | 2017-02-16 | Regular update
151 | 2017-02-23 | Regular update
152 | 2017-03-01 | Regular update
153 | 2017-03-09 | Regular update
154 | 2017-03-16 | Regular update
155 | 2017-03-23 | Regular update
156 | 2017-03-30 | Regular update
157 | 2017-04-06 | Regular update
158 | 2017-04-13 | Regular update
159 | 2017-04-20 | Regular update
160 | 2017-05-04 | Regular update
161 | 2017-05-11 | Regular update
162 | 2017-05-18 | Regular update
163 | 2017-05-25 | Regular update
164 | 2017-06-01 | Regular update
165 | 2017-06-08 | Regular update
166 | 2017-06-15 | Regular update
167 | 2017-06-22 | Regular update
168 | 2017-06-30 | Regular update
169 | 2017-07-06 | Regular update
170 | 2017-07-13 | Regular update
171 | 2017-07-21 | Regular update
172 | 2017-07-28 | Regular update
173 | 2017-08-03 | Regular update
174 | 2017-08-10 | Regular update
175 | 2017-08-17 | Regular update
176 | 2017-08-24 | Regular update
177 | 2017-08-31 | Regular update
178 | 2017-09-07 | Regular update
179 | 2017-09-14 | Regular update
180 | 2017-09-21 | Regular update
181 | 2017-09-28 | Regular update
182 | 2017-10-05 | Regular update
183 | 2017-10-11 | Regular update
184 | 2017-10-19 | Regular update
185 | 2017-10-26 | Regular update
186 | 2017-11-02 | Regular update
187 | 2017-11-09 | Regular update
188 | 2017-11-16 | Regular update
189 | 2017-11-23 | Regular update
190 | 2017-11-30 | Regular update
191 | 2017-12-07 | Regular update
192 | 2017-12-14 | Regular update
193 | 2017-12-20 | Regular update
194 | 2018-01-18 | Regular update
195 | 2018-01-25 | Regular update
196 | 2018-02-02 | Regular update
197 | 2018-02-08 | Regular update
198 | 2018-02-16 | Regular update
199 | 2018-02-22 | Regular update
200 | 2018-03-01 | Regular update
201 | 2018-03-09 | Regular update
202 | 2018-03-15 | Regular update
203 | 2018-03-22 | Regular update
204 | 2018-03-29 | Regular update
205 | 2018-04-05 | Regular update
206 | 2018-04-12 | Regular update
207 | 2018-04-19 | Regular update
208 | 2018-04-26 | Regular update
209 | 2018-05-03 | Regular update
210 | 2018-05-10 | Regular update
211 | 2018-05-17 | Regular update
212 | 2018-05-24 | Regular update
213 | 2018-05-31 | Regular update
214 | 2018-06-07 | Regular update
215 | 2018-06-14 | Regular update
216 | 2018-06-21 | Regular update
217 | 2018-06-28 | Regular update
218 | 2018-06-29 | Regular update
219 | 2018-07-12 | Regular update
220 | 2018-07-19 | Regular update
221 | 2018-07-26 | Regular update
222 | 2018-08-02 | Regular update
223 | 2018-08-16 | Regular update
224 | 2018-08-17 | Regular update
225 | 2018-09-13 | Regular update
226 | 2018-10-04 | Regular update
227 | 2018-10-18 | Regular update
228 | 2018-11-01 | Regular update
229 | 2018-11-22 | Regular update
230 | 2018-12-06 | Regular update
231 | 2018-12-20 | Regular update
232 | 2019-01-10 | Regular update
233 | 2019-01-24 | Regular update
234 | 2019-02-07 | Regular update
235 | 2019-02-21 | Regular update
236 | 2019-03-07 | Regular update
237 | 2019-03-21 | Regular update
238 | 2019-04-04 | Regular update
239 | 2019-05-09 | Regular update
240 | 2019-05-23 | Regular update
241 | 2019-06-06 | Regular update
242 | 2019-06-20 | Regular update
243 | 2019-07-04 | Regular update
244 | 2019-07-26 | Regular update
245 | 2019-08-08 | Regular update
246 | 2019-08-22 | Regular update
247 | 2019-09-05 | Regular update
248 | 2019-09-19 | Regular update
249 | 2019-10-02 | Regular update
250 | 2019-10-17 | Regular update
251 | 2019-11-07 | Regular update
252 | 2019-11-22 | Regular update
253 | 2019-12-05 | Regular update
254 | 2019-12-19 | Regular update
255 | 2020-01-23 | Regular update
256 | 2020-02-06 | Regular update
257 | 2020-04-30 | Anna Bay added
258 | 2020-05-15 | Regular update
259 | 2020-06-12 | Regular update
260 | 2020-06-25 | Regular update
261 | 2020-07-30 | Regular update
262 | 2020-08-27 | Regular update
263 | 2020-09-29 | Regular update
264 | 2020-10-28 | Regular update
265 | 2020-11-30 | Regular update
266 | 2021-02-09 | No changes
267 | 2021-03-02 | No changes